## Slide 1
Welsh Government
Hwb Update
16 May 2014
Notes: 1

## Slide 2
Hwb / Hwb+ updates
Hwb+ training
Hwb+ roll out
Microsoft Office365
Hwb+ key milestones
National Digital Content Repository
HwbMeets
e-Safety

## Slide 3
Hwb+ training
To date:
  824 schools ( CSC 243, ERW 226 EAS 142, North 213)
  1147 trained users
  Tranche 5 training commenced 9 April
  TSec training commenced 6 May
  81 training sessions – up to 1215 teachers
  All schools will have opportunity to attend a training session before the end of the academic year

## Slide 4: Hwb+ rollout update
  April 2014 – SWGfL led e-Safety awareness raising sessions (including Office365)
  May 2014 – Commenced secondary school training, local authorities (LAs) and regional education consortia (RECs) have identified priorities
  July 2014 - By the end of academic year, only a small number of schools will not have been provisioned.

## Slide 5: Office365 update
  Rollout completion dates:
    Tranche 4 schools completed ahead of schedule
    Tranche 5 completed ahead of schedule.
    Rollout of O365 to secondary schools in line with provisioning of Tranche Secondary

## Slide 6: Hwb+ key milestones (all on track)
  June 2014 – Office365 rollout complete
  July 2014 – commitment for all users to be provisioned on Hwb+ (based on LAs providing data by agreed deadlines)
  September/October 2014 – public school sites to be rolled out
  September 2014 – scoping for parent and governor sites commences

## Slide 7: National Digital Content Repository update
      Hosting arrangements have passed initial security assessment
      Progress being made regarding new content page designs and authentication

## Slide 8
HwbMeets
Two highly successful Cardiff events – 6 March and 6 April
Next event – Merthyr 15 May
Future events in Bridgend, Anglesey, Deeside, Porthmadog and will include specific focus such as the Literacy and Numeracy Framework, Arts in Education Review, SEN and FE

## Slide 9
Digital Content Event 8 May
Pilot event –to inform a programme of events for 2014/15 academic year
Held at Ysgol Plasmawr, Cardiff
Arts focus, with teachers working in groups
Groups included teachers, external experts from arts organisations, and an experienced facilitator familiar with the new Hwb content creation tools
Input from EAS
Event filmed with a view to creating a promotional video for the new Hwb community area

## Slide 10
e-Safety update
SWGfL Digital Literacy Resource and 360 degree safe: Cymru will be piloted in sample schools in September and launched in October 2014 via consortia launches.
QA workshops being arranged for June for 360 tool; QA of Digital Literacy resource internal to WG.
4 e-Safety live briefings already delivered in Ynys Môn, Wrexham, Merthyr Tydfil and Swansea
4 more events being organised for September in mid Wales and South Wales.

## Slide 11: e-Safety update
  Monthly programme of webinars launched
    May 12th – General awareness of e-Safety
    June 18th – Parental engagement
  E-Safety zone on Hwb updated to include SWGfL input – newsletter, parents area, e-Safety updates
  Ongoing work with Socitm, LAs, Safeguarding team and UAs to develop an all-Wales framework agreement governing web access for school-based learners and staff.

## Slide 12
www.cymru.gov.uk
Chris Owen
Digital Learning Division
christopher.owen2@wales.gsi.gov.uk
0300 7904574
hwb@wales.gsi.gov.uk
#hwbdysgu