## 4 June 2014
Ref | Agenda Item | Action | Owner | Status | Resolution Date | Update
122 | 1 Minutes, actions and matters arising from the meeting on 18 March 2014 | WG to amend procedures to ensure that guidance notes for all collections are made available as early as possible on the SDF site. | WG | Closed | 2014-11-01 | Implemented for Post-16
123 | 3 EYDAF and Curriculum Review | WG to consider impact of EYDAF on CTF. | WG | Open
124 | 4 NDC & National Tests 2015 | Suppliers to confirm that this change can be implemented. | Suppliers | Open |  | Confirmation from Advanced Learning and Capita received - 10/11/2014
125 | 4 NDC & National Tests 2015 | CHo to add the import file structure to the specification and publish on the SDF site. | WG - CHo | Closed | 2014-06-13 | Released to SDF site
126 | 4 NDC & National Tests 2015 | CHo to ensure that historical components are retained in the Excel versions of A_COMP and that only the current year's components are included in the specification. | WG - CHo | Closed | 2014-06-13 | Released to SDF site
127 | 4 NDC & National Tests 2015 | WG to provide 2013 test data to LAs. | WG | Open
128 | 4 NDC & National Tests 2015 | WG to provide clear communications on the revision of 2013 reading test scores. | WG | Open
129 | 4 NDC & National Tests 2015 | WG to work with suppliers to ensure revised scores are delivered to schools as soon as possible with clear instructions. | WG | Open
130 | 4 NDC & National Tests 2015 | SH to distribute revised quartiles. | WH - SH
131 | 4 NDC & National Tests 2015 | WG to respond to Mike's query. [language of test] | WG | Closed | 2014-06-06 | KAS confirmed data to be submitted for this pupil.
132 | 4 NDC & National Tests 2015 | CHo to confirm xsd filesets for summer 2015. | WG - CHo | Closed | 2014-06-10 | Confirmed by email.
133 | 5 Post-16 2015 | AO to include line in specification that software does not have to validate activities within programmes. | WG - AO | Closed | 2014-07-15 | Included in Post-16 spec (Version 2.0)
134 | 5 Post-16 2015 | AO to provide LAs information on the changes to the post-16 collection. | WG - AO | Closed | 2014-06-12 | Email from Sian James to LAs
135 | 5 Post-16 2015 | WG to consider validation rules. | WG - SJ | Closed | 2014-08-04 | Validation CBDS v1516.0.0 released to SDF site, including validation rules for some programmes.
136 | 5 Post-16 2015 | WG to clarify in the specification if subjects are being recorded but not used for performance. | WG - AO | Closed | 2014-07-15 | Policy team confirmed that data on all activites from 01/09 each year are to be included in the return
137 | 5 Post-16 2016 | Suppliers to notify schools not to change the year taught data item until September. | Suppliers | Open |  | Confirmation from Advanced Learning and Capitareceived - 10/11/2014
138 | 6 2014 Performance Tables | SH to share stakeholder survey results with SDF. | WG - SH | Closed | 2014-11-10 | Link to stakeholder survey sent to SDF mailing list.
139 | 6 2014 Performance Tables | SH to share the mapping table for Wales. | WG - SH | Open |  | 07/11/2014 - No decisions have been made yet as to what the 2015 list will look like.
140 | 6 2014 Performance Tables | SH to review the outcome and advise SDF of any implications for summary reports that suppliers may provide in their systems. | WG - SH | Open |  | 07/11/2014 - impact of survey results will happen in 2016
141 | 7 EOTAS 2016 | WG to consider the double counting issue when including exclusions in the EOTAS 2016 draft specification. | WG - CHo | Open
142 | 8 XSLT fileset naming convention | WG to trial release note with next release of new xslt filesets. | WG | Closed |  | Completed for Jan 2015 XSLT
143 | 9 SDF Cycle | CHo to send out more information on the changes. | WG - CHo | Closed | 2014-06-09 | Email with details of the change sent to SDF
144 | 11 AOB | WG to contact LAs for feedback on this item. [penalty notices] | WG - CHo | Open
145 | 11 AOB | CHo to get in touch with LH to resolve the query. [action 103, exceptions] | WG - CHo | Closed | 2014-06-05 | Query passed to policy team for response
146 | 11 AOB | CHo to get in touch with LH to resolve the query. [ULN] | WG - CHo | Closed | 2014-06-18 | Resolved between WG, RM, LA and school

## 18 March 2014
Ref | Agenda Item | Action | Owner | Status | Resolution Date | Update
100 | 3. Jan. PLASC 2015 Amended Specification | Review School Governance in PLASC after PLASC 2015 | WG - CHo | Open
104 | 3. Jan. PLASC 2015 Amended Specification | Arrange a review of summary reports | WG - CHo | Open
105 | 4. EOTAS 2015 Amended Specification | Provide information on EOTAS funding and the prevention of double counting between main and EOTAS provisions | WG - SHu | Closed | 2014-06-04 | SH confirmed that there are a number of checks in place to prevent double counting at the SDF meeting on 04/06/14.
108 | 4. EOTAS 2015 Amended Specification | Provide guidance on SEN rankings in PLASC and EOTAS | WG - CHo | Closed | 2014-06-04 | CHo confirmed that this will be included in guidance for PLASC & EOTAS 2015 at the SDF meeting on 04/06/14.
110 | 5. NDC and National Tests | WG confirm file formats for NDC file downloads from DEWi | WG - CHo | Open |  | CHo requested more information on this at the SDF meeting on 04/06/14 and will now work with suppliers to ensure LAs are able to import tests data for 2015
112 | 6. Post-16 2015 Draft Specification | WG inform schools of the post-16 changes | WG - AO | Open
114 | 6. Post-16 2015 Draft Specification | Post-16 Technical Completion Notes to be made available to suppliers/ uploaded to DEWi SDF | WG - AO | Closed | 2014-07-01 | Completion notes for 2014 released to SDF site
115 | 6. Post-16 2015 Draft Specification | New summary reports should include blank/zero lines | WG - AO | Closed | 2014-06-04 | AO advised that this would not be feasible at the SDF meeting on 04/06/14.
116 | 6. Post-16 2015 Draft Specification | Post-16 Technical Completion Notes to state which pupils should be included in the return | WG - AO | Closed | 2014-07-01 | Included in completion notes
117 | 6. Post-16 2015 Draft Specification | WG to provide guidance on mature learners, the P-16 collection and UPNs | WG | Open |  | To be Included in completion notes
118 | 6. Post-16 2015 Draft Specification | WG to provide mapping table to the SDF and LA Data/IMS teams | WG - AO | Closed | 2014-06-04 | AO advised that this would not be feasible at the SDF meeting on 04/06/14.
119 | 6. Post-16 2015 Draft Specification | A link to the mapping table to be included in Post-16 Completion Notes | WG - AO | Closed | 2014-06-04 | As action 118.
120 | 7. XSLT fileset naming convention | WG to review fileset numbering | WG - CHo | Closed | 2014-06-04 | Discussed at the SDF meeting on 04/06/14 and agreed to trial new fileset release note with January 2015 xslt files.
121 | 8. A.O.B. | WG to research the issue of commas within pupil names | WG - CHo | Open |  | CHo requested more information on this at the SDF meeting on 04/06/14 and will now work with Method4 to ensure the issue can be resolved.

## 11 February 2014
Ref | Agenda item | Action | Owner | Status | Resolution Date | Update
92 | 6 Post-16 | Provide a mapping table for Activities to Programmes | WG - AO | Closed | 2014-06-04 | Duplication of actions 118 and 119.
96 | 10 Response Times | Revised approach to response times to be reviewed in 3 months | WG - CHo | Closed | 2014-06-04 | Reviewed at SDF meeting on 04/06/14 and agreed that there has been an improvement and that the action could be re-opened if necessary in future.
97 | 10 Response Times | Investigate the use the of issues log within DEWi for supplier queries | WG - CHo | Closed | 2014-06-04 | Can be re-opened in future if deemed necessary, see action 96.

## 1 July 2013
Ref | Agenda item | Action | Owner | Status | Resolution Date | Update
68 | 7 Any Other Business | Provide PLASC data to Cardiff and Swansea to investigate discrepancies on the calculation of fixed-term exclusions | WG - SHu/MS | Open | 2014-07-01 | Three local authorities were sent their data to compare in July, but we have still not heard back from them 10/11/14.

## All Open Actions
Ref | Date Raised | Agenda Item | Action | Owner | Update
100 | 2014-03-18 | 3. Jan. PLASC 2015 Amended Specification | Review School Governance in PLASC after PLASC 2015 | CHo
104 | 2014-03-18 | 3. Jan. PLASC 2015 Amended Specification | Arrange a review of summary reports | CHo
110 | 2014-03-18 | 5. NDC and National Tests | WG confirm file formats for NDC file downloads from DEWi | CHo | CHo requested more information on this at the SDF meeting on 04/06/14 and will now work with suppliers to ensure LAs are able to import tests data for 2015
112 | 2014-03-18 | 6. Post-16 2015 Draft Specification | WG inform schools of the post-16 changes | AO
117 | 2014-03-18 | 6. Post-16 2015 Draft Specification | WG to provide guidance on mature learners, the P-16 collection and UPNs | WG | To be included in Completion notes
121 | 2014-03-18 | 8. A.O.B. | WG to research the issue of commas within pupil names | WG | CHo requested more information on this at the SDF meeting on 04/06/14 and will now work with Method4 to ensure the issue can be resolved.
123 | 2014-06-05 | 3 EYDAF and Curriculum Review | WG to consider impact of EYDAF on CTF. | WG
124 | 2014-06-06 | 4 NDC & National Tests 2015 | Suppliers to confirm that this change can be implemented. | Suppliers | Confirmation from Advanced Learning and Capita received - 10/11/2014
127 | 2014-06-07 | 4 NDC & National Tests 2015 | WG to provide 2013 test data to LAs. | WG
128 | 2014-06-08 | 4 NDC & National Tests 2015 | WG to provide clear communications on the revision of 2013 reading test scores. | WG
129 | 2014-06-09 | 4 NDC & National Tests 2015 | WG to work with suppliers to ensure revised scores are delivered to schools as soon as possible with clear instructions. | WG
130 | 2014-06-10 | 4 NDC & National Tests 2015 | SH to distribute revised quartiles. | WH - SH
137 | 2014-06-13 | 5 Post-16 2016 | Suppliers to notify schools not to change the year taught data item until September. | Suppliers | Confirmation from Advanced Learning and Capitareceived - 10/11/2014
139 | 2014-06-15 | 6 2014 Performance Tables | SH to share the mapping table for Wales. | WG - SH | 07/11/2014 - No decisions have been made yet as to what the 2015 list will look like.
140 | 2014-06-16 | 6 2014 Performance Tables | SH to review the outcome and advise SDF of any implications for summary reports that suppliers may provide in their systems. | WG - SH | 07/11/2014 - impact of survey results will happen in 2016
141 | 2014-06-17 | 7 EOTAS 2016 | WG to consider the double counting issue when including exclusions in the EOTAS 2016 draft specification. | WG - CHo
144 | 2014-06-19 | 11 AOB | WG to contact LAs for feedback on this item. [penalty notices] | WG - CHo

## Recently Closed Actions
Ref | Date Raised | Agenda item | Action | Owner | Resolution Date | Update
68 | 2013-07-01 | 7 Any Other Business | Provide PLASC data to Cardiff and Swansea to investigate discrepancies on the calculation of fixed-term exclusions | WG - SHu/MS | 2014-07-01 | Three local authorities were sent their data to compare in July, but we have still not heard back from them 10/11/14.
92 | 2014-02-11 | 6 Post-16 | Provide a mapping table for Activities to Programmes | WG - AO | 2014-06-04 | Duplication of actions 118 and 119.
96 | 2014-02-11 | 10 Response Times | Revised approach to response times to be reviewed in 3 months | WG - CHo | 2014-06-04 | Reviewed at SDF meeting on 04/06/14 and agreed that there has been an improvement and that the action could be re-opened if necessary in future.
97 | 2014-02-11 | 10 Response Times | Investigate the use the of issues log within DEWi for supplier queries | WG - CHo | 2014-06-04 | Can be re-opened in future if deemed necessary, see action 96.
105 | 2014-03-18 | 4. EOTAS 2015 Amended Specification | Provide information on EOTAS funding and the prevention of double counting between main and EOTAS provisions | WG - SHu | 2014-06-04 | SH confirmed that there are a number of checks in place to prevent double counting at the SDF meeting on 04/06/14.
108 | 2014-03-18 | 4. EOTAS 2015 Amended Specification | Provide guidance on SEN rankings in PLASC and EOTAS | WG - CHo | 2014-06-04 | CHo confirmed that this will be included in guidance for PLASC & EOTAS 2015 at the SDF meeting on 04/06/14.
114 | 2014-03-18 | 6. Post-16 2015 Draft Specification | Post-16 Technical Completion Notes to be made available to suppliers/ uploaded to DEWi SDF | WG - AO | 2014-07-01 | Completion notes for 2014 released to SDF site
115 | 2014-03-18 | 6. Post-16 2015 Draft Specification | New summary reports should include blank/zero lines | WG - AO | 2014-06-04 | AO advised that this would not be feasible at the SDF meeting on 04/06/14.
116 | 2014-03-18 | 6. Post-16 2015 Draft Specification | Post-16 Technical Completion Notes to state which pupils should be included in the return | WG - AO | 2014-07-01 | Included in completion notes
118 | 2014-03-18 | 6. Post-16 2015 Draft Specification | WG to provide mapping table to the SDF and LA Data/IMS teams | WG - AO | 2014-06-04 | AO advised that this would not be feasible at the SDF meeting on 04/06/14.
119 | 2014-03-18 | 6. Post-16 2015 Draft Specification | A link to the mapping table to be included in Post-16 Completion Notes | WG - AO | 2014-06-04 | As action 118.
120 | 2014-03-18 | 7. XSLT fileset naming convention | WG to review fileset numbering | WG - CHo | 2014-06-04 | Discussed at the SDF meeting on 04/06/14 and agreed to trial new fileset release note with January 2015 xslt files.
122 | 2014-06-04 | 1 Minutes, actions and matters arising from the meeting on 18 March 2014 | WG to amend procedures to ensure that guidance notes for all collections are made available as early as possible on the SDF site. | WG | 2014-11-01 | Implemented for Post-16
125 | 2014-06-04 | 4 NDC & National Tests 2015 | CHo to add the import file structure to the specification and publish on the SDF site. | WG - CHo | 2014-06-13 | Released to SDF site
126 | 2014-06-04 | 4 NDC & National Tests 2015 | CHo to ensure that historical components are retained in the Excel versions of A_COMP and that only the current year's components are included in the specification. | WG - CHo | 2014-06-13 | Released to SDF site
131 | 2014-06-04 | 4 NDC & National Tests 2015 | WG to respond to Mike's query. [language of test] | WG | 2014-06-06 | KAS confirmed data to be submitted for this pupil.
132 | 2014-06-04 | 4 NDC & National Tests 2015 | CHo to confirm xsd filesets for summer 2015. | WG - CHo | 2014-06-10 | Confirmed by email.
133 | 2014-06-04 | 5 Post-16 2015 | AO to include line in specification that software does not have to validate activities within programmes. | WG - AO | 2014-07-15 | Included in Post-16 spec (Version 2.0)
134 | 2014-06-04 | 5 Post-16 2015 | AO to provide LAs information on the changes to the post-16 collection. | WG - AO | 2014-06-12 | Email from Sian James to LAs
135 | 2014-06-04 | 5 Post-16 2015 | WG to consider validation rules. | WG - SJ | 2014-08-04 | Validation CBDS v1516.0.0 released to SDF site, including validation rules for some programmes.
136 | 2014-06-04 | 5 Post-16 2015 | WG to clarify in the specification if subjects are being recorded but not used for performance. | WG - AO | 2014-07-15 | Policy team confirmed that data on all activites from 01/09 each year are to be included in the return
138 | 2014-06-04 | 6 2014 Performance Tables | SH to share stakeholder survey results with SDF. | WG - SH | 2014-11-10 | Link to stakeholder survey sent to SDF mailing list.
142 | 2014-06-04 | 8 XSLT fileset naming convention | WG to trial release note with next release of new xslt filesets. | WG |  | Completed for Jan 2015 XSLT
143 | 2014-06-04 | 9 SDF Cycle | CHo to send out more information on the changes. | WG - CHo | 2014-06-09 | Email with details of the change sent to SDF
145 | 2014-06-04 | 11 AOB | CHo to get in touch with LH to resolve the query. [action 103, exceptions] | WG - CHo | 2014-06-05 | Query passed to policy team for response
146 | 2014-06-04 | 11 AOB | CHo to get in touch with LH to resolve the query. [ULN] | WG - CHo | 2014-06-18 | Resolved between WG, RM, LA and school