| ACTIONS FROM MEETINGS |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Section in minutes | Action |  | Who | Status |  | Comments |
| Outcome of meeting held 12/06/2012 |  |  |  |  |  |  |  |
| 1 | 2 Mins of Prev Meeting | WG to provide suppliers with advance warning of exactly what examination entries data they would like to extract from schools’ MIS systems |  | WG - SH | Open |  |  |
| 2 | 2 Mins of Prev Meeting | Once received the requirement from WG regarding examinations data, Suppliers to flag up in their guidance to schools/LAs existing functionality that can be used to check the accuracy of this data before submission to WG |  | Suppliers | Open |  |  |
| 3 | 3 Class Size Paper | Where the number of home and guest pupils is 31 or more and there are no exceptions present, a query needs to be generated to state the class is in breach of regulation/WG recommendations |  | WG - ET | Closed | Incorporated into Val CBDS v1213.2.0 |  |
| 4 | 3 Class Size Paper | Modular CBDS to be updated to make clear that the exception relates to the class at school level and not an individual pupil level |  | WG - ET | Closed | Incorporated into School Modular CBDS v1213.1.1 to be released shortly |  |
| 5 | 3 Class Size Paper | WG to re-issue the old class size exception spreadsheet to the group |  | WG - ET | Closed | Issued 28/06/12 |  |
| 6 | 3 Class Size Paper | WG to update the xml example in the class size paper to make it correct and re-issue to the group |  | WG - ET | Closed | Issued 28/06/12 |  |
| 7 | 3 Class Size Paper | Suppliers to respond by Friday 22nd June confirming they understand what WG are trying to achieve and confirming that they can implement for January 2013 with no issues |  | Suppliers | Open |  |  |
| 8 | 3 Class Size Paper | SH to write to schools by the end of term regarding integrating the class size collection into January PLASC |  | WG - SH | Open |  |  |
| 9 | 4 Middle Schools | WG to consult with Capita & schools involved regarding how the middle schools functionality can be provided |  | WG | Open |  |  |
| 10 | 4 Middle Schools | WG to amend PLASC 2013 specification, Modular CBDS, XSLT Validation rules and DEWi for Middle schools |  | WG - ET | Open |  |  |
| 11 | 4 Middle Schools | WG to let suppliers know if any other schools are thinking of changing to Middle schools |  | WG | Open |  |  |
| 12 | 4 Middle Schools | JH will contact the 4 schools for September 2012 again, once the spec has been produced, to discuss implementation |  | JH | Open |  |  |
| 13 | 4 Middle Schools | SH to confirm whether a new database is required for new schools or not |  | WG - SH | Open |  |  |
| 14 | 5 NDC Spec incl. NRT | WG to forward link to the group for consultation on the Literacy and Numeracy Framework |  | WG - ET | Closed | Sent 15/06/12 |  |
| 15 | 5 NDC Spec incl. NRT | ET to check if reading age equivalent is defined in England’s CBDS |  | WG - ET | Open |  |  |
| 16 | 5 NDC Spec incl. NRT | ET to update Modular CBDS for the National Reading Test |  | WG - ET | Closed | Will be released shortly |  |
| 17 | 5 NDC Spec incl. NRT | AS to add ‘CYM’ as a valid response to CBDS item P148, of the NRT school output example file |  | WG - AS | Closed | Added 26/06/12 |  |
| 18 | 5 NDC Spec incl. NRT | EW/AS to confirm whether standardised and progress scores by age group will be defined in A-COMP or Modular CBDS |  | WG - EW/AS | Closed | Confirmed these should be added to A_COMP. Added 26/06/12 |  |
| 19 | 5 NDC Spec incl. NRT | Suppliers to provide feedback on draft NDC 0.2 spec by 25th June |  | Suppliers | Closed |  |  |
| 20 | 5 NDC Spec incl. NRT | WG to provide a link to the new parents guide to the group |  | WG | Open | Sent to group 28/06/12 |  |
| 21 | 5 NDC Spec incl. NRT | WG to release final NDC specification on 27th June 2012 |  | WG - AS | Closed | Released 26/06/12 |  |
| 22 | 6 AOB | NB to provide WG with a contact for the RM user group |  | NB - SERCO | Open |  |  |
| 23 | 6 AOB | Group to feedback on the draft Terms of Reference by 26th June 2012 |  | Group | Open | No responses received |  |
| 24 | 6 AOB | Group to confirm their attendance at the next meeting with Patrick Sullivan |  | Group | Open |  |  |
| Outcome of meeting held 15/03/2012 |  |  |  |  |  |  |  |
| 25 | 3 NDC 2013 draft spec | JW to amend spec from NC year to age |  | AS | Closed | EW confirmed this is NC year |  |
| 26 | 3 NDC 2013 draft spec | WG to provide suppliers with any draft/update documents referring to reading and numeracy tests |  | WG | Closed | WG to provide link to the consultation |  |
| 27 | 3 NDC 2013 draft spec | Suppliers to confirm that they can support the use of raw scores |  | Suppliers | Open | Capita/Serco confirmed. RM to confirm |  |
| 28 | 3 NDC 2013 draft spec | RM to review CTF issues and respond to WG |  | RM - AF | Open |  |  |
| 29 | 3 NDC 2013 draft spec | JW to add footnote in spec referring to NC outcomes 1-6 |  | JW | Closed | Software suppliers can choose to include these |  |
| 30 | 3 NDC 2013 draft spec | EW to look at best way of transferring NDC file - by year group/all pupils |  | WG - EW | Closed | EW confirmed one file for all eligible pupils in school. |  |
| 31 | 3 NDC 2013 draft spec | EW to determine procedures on how to deal with if a pupil misses a test |  | EW | Closed | EW code X introduced for absent. |  |
| 32 | 4 January PLASC 2013 Spec | JH to investigate the Exclusion sessions restriction |  | JH | Open |  |  |
| 33 | 4 January PLASC 2013 Spec | YD to provide WG with query regarding Primary summary report 3.3 |  | YD | Closed |  |  |
| Outcome of meeting held 16/02/2012 |  |  |  |  |  |  |  |
| 34 | 4 Code Z | KR to remove Code Z from guidance |  | WG (KR) | Open | Inclusion & Pupil Support Guid. to be re-issued Dec 12 |  |
| 35 | 4 Code Z | KR to revise the guidance on the use of codes X and Y |  | WG (KR) | Open | As above |  |
| 36 | 4 Dual Registration | WG to provide the requirement regarding the dual registration issue to suppliers |  | WG (KR/EG) | Open | Currently being prepared to be issued to suppliers shortly |  |
| 37 | 4 Dual Registration | Suppliers to provide WG with options on how to solve dual registration issue, once requirement is received |  | Suppliers | On hold | On hold until requirement is received from WG |  |
| 38 | 4 Exclusions | WG to release updated exclusions guidance |  | WG - OV | Open | Due in June |  |
| Outcome of meeting held 08/11/2011 |  |  |  |  |  |  |  |
| 39 | 6 AOB (Exam Entries) | SH to email suppliers on exam entries to check whether anything has changed since their original response in July, and suppliers to respond accordingly. |  | WG (SH)/ Suppliers | Closed | Discussed at June SDF. |  |
| Outcome of meeting held 04/10/2011 |  |  |  |  |  |  |  |
| 40 | 3 Sept P16 2012 spec | WG to look into new validation rules for ULN for P-16 as this will be different to PLASC | WG |  | Open | Will be p/art of the next Sept P-16 development |  |
| 41 | 6 AOB – Dual registration | KR to release guidance on new dual registration procedures, and enrolment status, including various scenarios | WG (KR) |  | Open | Inclusion & Pupil Support Guid. to be re-issued Dec 12 |  |