## Version Control
Information relating to this document
Title | Software Development Cycle
Version | Version 1.0
Filename | Software Development Cycle
Creator | Gav Elias
Audience | Software Development Forum and educational software suppliers
Availability | Software Development Forum pages on DEWi
Description | This workbook contains the the planned timelines for the work schedules related to the development of the educational statutory data collections in Wales from the 2023/2024 academic year onwards
Subject category | Information Management
Date last updated | 2023-09-28
Notes | Please note that this document will be continuously updated throughout the development cycle as necessary. When a new version is created, it will have a new version number and entries on the Change log tab to detail what has changed
Please send all queries to IMS@wales.gsi.gov.uk
Activites covered by this document
This document details the timelines for the Data Collections Team's technical products such as Software Specifications, Common Basic Data Sets (CBDS'), and Technical Completion Notes for:
- | Attendance: Primary
- | Attendance: Secondary
- | Common Transfer File (CTF)
- | Educated Otherwise Than At School (EOTAS)
- | Modular Common Basic Data Set (Modular CBDS)
- | National Data Collection (NDC)
- | Post-16
- | Pupil Level Annual School Census (PLASC)
- | School Workforce Annual census (SWAC)
- | Validation Common Basic Data Set (Validation CBDS)
- | Welsh Examinations Database (WED)
Please use the individual tabs relating to each data collection or product for details.

## Key
Key to tab colours (NOTE: The tab for each data collection is in chronological order as the collections happen related to a particular academic year)
Metadata and generic information
Changes made to the document
Software Development Forum (SDF) meetings
Attendance (Primary and Secondary) data collection
Common Transfer File (CTF)
Educated Otherwise Than At School (EOTAS) data collection
Modular Common Basic Data Set (Modular CBDS)
National Data Collection (NDC)
Post-16 data collection
Pupil Level Annual School Census (PLASC) data collection
School Workforce Annual Census (SWAC) data collection
Validation Common Basic Data Set (Validation CBDS)
Key to colour coding within each tab
Black text | This colour scheme denotes the planned date of delivery and that things are on track for this to be met
Black text | This colour scheme denotes that this work item has been delivered
White text | This colour scheme denotes that this work item is/was late and/or withdrawn
Key to schedule entries
Early | This means the work item will be delivered early in the month referred to
Mid | This means the work item will be delivered in the middle of the month referred to
Late | This means the work item will be delivered late in the month referred to
CHRONOLOGY OF DATA COLLECTION WINDOWS THROUGHOUT EACH ACADEMIC YEAR
September to October | Post-16
November to December | School Workforce Annual Census (SWAC)
January to March | Pupil Level Annual School Census (PLASC)
January to March | Educated Otherwise Than At School (EOTAS)
April to May | National Data Collection (NDC)
May to July | Attendance (Secondary)
July to September | Attendance (Primary)
ADDITIONAL NOTES
The Academic Year referred to on the left hand column of each tab refers to the academic year that the data being collected relates to.
The Welsh Government's statutory data collections work is split into 3 annual development cycles. These cycles are named according to academic year, release number, and iterative build, e.g., 2324.1.1 would be the 2023/2024 development for the first build in September, and would be the first iterative update after the baselined release. The collections included within each development are:
yyyy.1.n | School Workforce Annual Census (SWAC)
Post-16
yyyy.2.n | Pupil Level Annual School Census (PLASC)
Educated Otherwise Than At School (EOTAS)
yyyy.3.n | National Data Collection (NDC)
Attendance (Primary and Secondary)
NOTE: The Post-16 differs from other collections in that it is a retrospecitve data collection about the previous academic year

## Change log
Change log
Version | Release date | Issue |  | Tab(s) Affected
2324 | 2023-09-28 | 1 | Initial version of timeline document for the future statutory data collections development work schedules from the 2023/2024 academic year onwards | Version Control Key Change Log SDF Meetings CTF Modular CBDS Validation CBDS SWAC EOTAS PLASC Attendance NDC Post-16

## SDF Meetings
Software Development Forum (SDF) meetings
Academic Year | Activity/Output | Status |  |  |  |  | 2024 | [7 empty] | NOTES
|  |  | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG
2023/2024 | 2023/2024 Autumn Meeting | On track | OCT: 2023-10-03
| 2023/2024 Autumn Provisional Meeting | On track | NOV: 2023-11-07 | This will only take place if continued discussions are required after previous meeting
| 2023/2024 Spring Meeting | On track | 2024 FEB: 2024-02-06
| 2023/2024 Spring Provisional Meeting | On track | 2024 MAR: 2024-02-05 | This will only take place if continued discussions are required after previous meeting
| 2023/2024 Summer Meeting | On track | 2024 JUN: 2024-06-04
| 2023/2024 Summer Provisional Meeting | On track | 2024 JUL: 2024-07-09 | This will only take place if continued discussions are required after previous meeting
2024/2025 | 2024/2025 Autumn Meeting | On track | OCT: 2024-10-08
| 2024/2025 Autumn Provisional Meeting | On track | NOV: 2024-11-05 | This will only take place if continued discussions are required after previous meeting
| 2024/2025 Spring Meeting | On track | 2024 FEB: 2025-02-04
| 2024/2025 Spring Provisional Meeting | On track | 2024 MAR: 2025-03-04 | This will only take place if continued discussions are required after previous meeting
| 2024/2025 Summer Meeting | On track | 2024 JUN: 2025-06-10
| 2024/2025 Summer Provisional Meeting | On track | 2024 JUL: 2025-07-08 | This will only take place if continued discussions are required after previous meeting
2025/2026 | 2025/2026 Autumn Meeting | On track | OCT: 2025-10-07
| 2025/2026 Autumn Provisional Meeting | On track | NOV: 2025-11-04 | This will only take place if continued discussions are required after previous meeting
| 2025/2026 Spring Meeting | On track | 2024 FEB: 2026-02-03
| 2025/2026 Spring Provisional Meeting | On track | 2024 MAR: 2026-04-03 | This will only take place if continued discussions are required after previous meeting
| 2025/2026 Summer Meeting | On track | 2024 JUN: 2026-06-09
| 2025/2026 Summer Provisional Meeting | On track | 2024 JUL: 2026-07-07 | This will only take place if continued discussions are required after previous meeting
2026/2027 | 2026/2027 Autumn Meeting | On track | OCT: 2026-10-06
| 2026/2027 Autumn Provisional Meeting | On track | NOV: 2026-11-03 | This will only take place if continued discussions are required after previous meeting
| 2026/2027 Spring Meeting | On track | 2024 FEB: 2027-02-02
| 2026/2027 Spring Provisional Meeting | On track | 2024 MAR: 2027-03-02 | This will only take place if continued discussions are required after previous meeting
| 2026/2027 Summer Meeting | On track | 2024 JUN: 2027-06-08
| 2026/2027 Summer Provisional Meeting | On track | 2024 JUL: 2027-07-06 | This will only take place if continued discussions are required after previous meeting
2027/2028 | 2027/2028 Autumn Meeting | On track | OCT: 2027-10-05
| 2027/2028 Autumn Provisional Meeting | On track | NOV: 2027-11-02 | This will only take place if continued discussions are required after previous meeting
| 2027/2028 Spring Meeting | On track | 2024 FEB: 2028-02-08
| 2027/2028 Spring Provisional Meeting | On track | 2024 MAR: 2027-03-07 | This will only take place if continued discussions are required after previous meeting
| 2027/2028 Summer Meeting | On track | 2024 JUN: 2028-06-06
| 2027/2028 Summer Provisional Meeting | On track | 2024 JUL: 2028-07-04 | This will only take place if continued discussions are required after previous meeting

## CTF
Common Transfer File (CTF)
Academic Year | Activity/Output | Status | MONTH NOTE: These months are for the academic year preceding when the CTF takes effect) | [11 empty] | NOTES
|  |  | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG
2023/2024 | Software specification version 0.1 release | Delivered | MONTH NOTE: These months are for the academic year preceding when the CTF takes effect) DEC: Late | The CTF specification is issued by the DfE
| Software supplier specification review period ends | Delivered | MONTH NOTE: These months are for the academic year preceding when the CTF takes effect) JAN: Mid
| Software specification version 1.0 release | Delivered | MONTH NOTE: These months are for the academic year preceding when the CTF takes effect) JAN: Late | The CTF specification is issued by the DfE
| Schema file set version 1.0 release to suppliers | Delivered | MONTH NOTE: These months are for the academic year preceding when the CTF takes effect) FEB: Early | The Schema file set is issued by the DfE
2024/2025 | Software specification version 0.1 release | On track | MONTH NOTE: These months are for the academic year preceding when the CTF takes effect) DEC: Late | The CTF specification is issued by the DfE
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the academic year preceding when the CTF takes effect) JAN: Mid
| Software specification version 1.0 release | On track | MONTH NOTE: These months are for the academic year preceding when the CTF takes effect) JAN: Late | The CTF specification is issued by the DfE
| Schema file set version 1.0 release to suppliers | On track | MONTH NOTE: These months are for the academic year preceding when the CTF takes effect) FEB: Early | The Schema file set is issued by the DfE
2025/2026 | Software specification version 0.1 release | On track | MONTH NOTE: These months are for the academic year preceding when the CTF takes effect) DEC: Late | The CTF specification is issued by the DfE
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the academic year preceding when the CTF takes effect) JAN: Mid
| Software specification version 1.0 release | On track | MONTH NOTE: These months are for the academic year preceding when the CTF takes effect) JAN: Late | The CTF specification is issued by the DfE
| Schema file set version 1.0 release to suppliers | On track | MONTH NOTE: These months are for the academic year preceding when the CTF takes effect) FEB: Early | The Schema file set is issued by the DfE
2026/2027 | Software specification version 0.1 release | On track | MONTH NOTE: These months are for the academic year preceding when the CTF takes effect) DEC: Late | The CTF specification is issued by the DfE
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the academic year preceding when the CTF takes effect) JAN: Mid
| Software specification version 1.0 release | On track | MONTH NOTE: These months are for the academic year preceding when the CTF takes effect) JAN: Late | The CTF specification is issued by the DfE
| Schema file set version 1.0 release to suppliers | On track | MONTH NOTE: These months are for the academic year preceding when the CTF takes effect) FEB: Early | The Schema file set is issued by the DfE
2027/2028 | Software specification version 0.1 release | On track | MONTH NOTE: These months are for the academic year preceding when the CTF takes effect) DEC: Late | The CTF specification is issued by the DfE
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the academic year preceding when the CTF takes effect) JAN: Mid
| Software specification version 1.0 release | On track | MONTH NOTE: These months are for the academic year preceding when the CTF takes effect) JAN: Late | The CTF specification is issued by the DfE
| Schema file set version 1.0 release to suppliers | On track | MONTH NOTE: These months are for the academic year preceding when the CTF takes effect) FEB: Early | The Schema file set is issued by the DfE

## Modular CBDS
Modular Common Basic Data Set (Modular CBDS)
Academic Year | Activity/Output | Status | MONTH NOTE: These months are for the academic year preceding when the Modular CBDS takes effect) | [11 empty] | NOTES
|  |  | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG
2023/2024 | Modular CBDS 2324.0.1 release | Delivered | MONTH NOTE: These months are for the academic year preceding when the Modular CBDS takes effect) FEB: Early; MONTH NOTE: These months are for the academic year preceding when the Modular CBDS takes effect) MAY: Mid | Late due to review of sex, gender identitiy and school language categories
| Software supplier specification review period ends | Delivered | MONTH NOTE: These months are for the academic year preceding when the Modular CBDS takes effect) MAR: Mid; MONTH NOTE: These months are for the academic year preceding when the Modular CBDS takes effect) JUL: Mid | Late due to review of sex, gender identitiy and school language categories
| Modular CBDS 2324.1.0 release | Delivered | MONTH NOTE: These months are for the academic year preceding when the Modular CBDS takes effect) MAR: Late; MONTH NOTE: These months are for the academic year preceding when the Modular CBDS takes effect) JUL: Mid | Late due to review of sex, gender identitiy and school language categories
2024/2025 | Modular CBDS 2425.0.1 release | On track | MONTH NOTE: These months are for the academic year preceding when the Modular CBDS takes effect) FEB: Early
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the academic year preceding when the Modular CBDS takes effect) MAR: Mid
| Modular CBDS 2425.1.0 release | On track | MONTH NOTE: These months are for the academic year preceding when the Modular CBDS takes effect) MAR: Late
2025/2026 | Modular CBDS 2526.0.1 release | On track | MONTH NOTE: These months are for the academic year preceding when the Modular CBDS takes effect) FEB: Early
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the academic year preceding when the Modular CBDS takes effect) MAR: Mid
| Modular CBDS 2526.1.0 release | On track | MONTH NOTE: These months are for the academic year preceding when the Modular CBDS takes effect) MAR: Late
2026/2027 | Modular CBDS 2627.0.1 release | On track | MONTH NOTE: These months are for the academic year preceding when the Modular CBDS takes effect) FEB: Early
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the academic year preceding when the Modular CBDS takes effect) MAR: Mid
| Modular CBDS 2627.1.0 release | On track | MONTH NOTE: These months are for the academic year preceding when the Modular CBDS takes effect) MAR: Late
2027/2028 | Modular CBDS 2728.0.1 release | On track | MONTH NOTE: These months are for the academic year preceding when the Modular CBDS takes effect) FEB: Early
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the academic year preceding when the Modular CBDS takes effect) MAR: Mid
| Modular CBDS 2728.1.0 release | On track | MONTH NOTE: These months are for the academic year preceding when the Modular CBDS takes effect) MAR: Late

## Validation CBDS
Validation Common Basic Data Set (Validation CBDS)
Academic Year | Activity/Output | Status | MONTH NOTE: These months are for the academic year preceding when the Validation CBDS takes effect) | [19 empty] | NOTES
|  |  | SET | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR
2023/2024 | Validation CBDS 2324.0.1 release (base draft version) | Delivered | MONTH NOTE: These months are for the academic year preceding when the Validation CBDS takes effect) FEB: Early; MONTH NOTE: These months are for the academic year preceding when the Validation CBDS takes effect) JUN: Late | Late due to review of sex, gender identitiy and school language categories
| Software supplier specification review period ends | Delivered | MONTH NOTE: These months are for the academic year preceding when the Validation CBDS takes effect) MAR: Mid; MONTH NOTE: These months are for the academic year preceding when the Validation CBDS takes effect) JUL: Mid | Late due to review of sex, gender identitiy and school language categories
| Validation CBDS 2324.1.0 release (baselined version for September 2023 release) | Delivered | MONTH NOTE: These months are for the academic year preceding when the Validation CBDS takes effect) MAR: Late; MONTH NOTE: These months are for the academic year preceding when the Validation CBDS takes effect) JUL: Mid | Late due to review of sex, gender identitiy and school language categories
| Validation CBDS 2324.2.0 release (baselined version for January 2024 release) | Delivered | MONTH NOTE: These months are for the academic year preceding when the Validation CBDS takes effect) JUN: Late; MONTH NOTE: These months are for the academic year preceding when the Validation CBDS takes effect) SEP: Mid | Late due to review of sex, gender identitiy and school language categories
| Validation CBDS 2324.3.0 release (baselined version for April 2024 release) | On track | MONTH NOTE: These months are for the academic year preceding when the Validation CBDS takes effect) SEP: Mid; MONTH NOTE: These months are for the academic year preceding when the Validation CBDS takes effect) OCT: Mid | Late due to dependancy on preceding development builds
2024/2025 | Validation CBDS 2425.0.1 release (base draft version) | On track | MONTH NOTE: These months are for the academic year preceding when the Validation CBDS takes effect) FEB: Early
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the academic year preceding when the Validation CBDS takes effect) MAR: Mid
| Validation CBDS 2425.1.0 release (baselined version for September 2024 release) | On track | MONTH NOTE: These months are for the academic year preceding when the Validation CBDS takes effect) MAR: Late
| Validation CBDS 2425.2.0 release (baselined version for January 2025 release) | On track | MONTH NOTE: These months are for the academic year preceding when the Validation CBDS takes effect) JUN: Late
| Validation CBDS 2425.3.0 release (baselined version for April 2025 release) | On track | MONTH NOTE: These months are for the academic year preceding when the Validation CBDS takes effect) SEP: Mid
2025/2026 | Validation CBDS 2526.0.1 release (base draft version) | On track | MONTH NOTE: These months are for the academic year preceding when the Validation CBDS takes effect) FEB: Early
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the academic year preceding when the Validation CBDS takes effect) MAR: Mid
| Validation CBDS 2526.1.0 release (baselined version for September 2025 release) | On track | MONTH NOTE: These months are for the academic year preceding when the Validation CBDS takes effect) MAR: Late
| Validation CBDS 2526.2.0 release (baselined version for January 2026 release) | On track | MONTH NOTE: These months are for the academic year preceding when the Validation CBDS takes effect) JUN: Late
| Validation CBDS 2526.3.0 release (baselined version for April 2026 release) | On track | MONTH NOTE: These months are for the academic year preceding when the Validation CBDS takes effect) SEP: Mid
2026/2027 | Validation CBDS 2627.0.1 release (base draft version) | On track | MONTH NOTE: These months are for the academic year preceding when the Validation CBDS takes effect) FEB: Early
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the academic year preceding when the Validation CBDS takes effect) MAR: Mid
| Validation CBDS 2627.1.0 release (baselined version for September 2026 release) | On track | MONTH NOTE: These months are for the academic year preceding when the Validation CBDS takes effect) MAR: Late
| Validation CBDS 2627.2.0 release (baselined version for January 2027 release) | On track | MONTH NOTE: These months are for the academic year preceding when the Validation CBDS takes effect) JUN: Late
| Validation CBDS 2627.3.0 release (baselined version for April 2027 release) | On track | MONTH NOTE: These months are for the academic year preceding when the Validation CBDS takes effect) SEP: Mid
2027/2028 | Validation CBDS 2728.0.1 release (base draft version) | On track | MONTH NOTE: These months are for the academic year preceding when the Validation CBDS takes effect) FEB: Early
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the academic year preceding when the Validation CBDS takes effect) MAR: Mid
| Validation CBDS 2728.1.0 release (baselined version for September 2027 release) | On track | MONTH NOTE: These months are for the academic year preceding when the Validation CBDS takes effect) MAR: Late
| Validation CBDS 2728.2.0 release (baselined version for January 2028 release) | On track | MONTH NOTE: These months are for the academic year preceding when the Validation CBDS takes effect) JUN: Late
| Validation CBDS 2728.3.0 release (baselined version for April 2028 release) | On track | MONTH NOTE: These months are for the academic year preceding when the Validation CBDS takes effect) SEP: Mid

## SWAC
School Workforce Annual Census (SWAC)
Academic Year | Activity/Output | Status | MONTH NOTE: These months are for the year preceding and building up to the SWAC data collection) | [11 empty] | NOTES
|  |  | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
2023/2024 | Software specification version 0.1 release | Delivered | FEB: Early; MAR: Early
| Software supplier specification review period ends | Delivered | MAR: Mid; JUN: Late | Late due to work required for school language categories
| Software specification version 1.0 release | Delivered | MAR: Late; JUN: Late | Late due to work required for school language categories
| Schema, Summary, and Validation XSLT file set development by the Welsh Government | Delivered | MAY: Mid; JUN: Late | Late due to work required for school language categories
| Schema, Summary, and Validation XSLT file set beta version (untested) release to suppliers | Delivered | JUN: Early; JUL: Late | Late due to work required for school language categories
| Schema, Summary, and Validation XSLT file set version 1.0 (tested) release to suppliers | Delivered | JUL: Early; AUG: Mid | Late due to work required for school language categories
| Technical Completion Notes v1.0 release | Delivered | AUG: Late; SEP: Mid | Late due to work related to sex and school language categories
| SWAC data collection window start | On track | NOV: Early
| SWAC data collection window end | On track | DEC: Mid
2024/2025 | Software specification version 0.1 release | On track | FEB: Early
| Software supplier specification review period ends | On track | MAR: Mid
| Software specification version 1.0 release | On track | MAR: Late
| Schema, Summary, and Validation XSLT file set development by the Welsh Government | On track | MAY: Mid
| Schema, Summary, and Validation XSLT file set beta version (untested) release to suppliers | On track | JUN: Early
| Schema, Summary, and Validation XSLT file set version 1.0 (tested) release to suppliers | On track | JUL: Early
| Technical Completion Notes v1.0 release | On track | AUG: Late
| SWAC data collection window start | On track | NOV: Early
| SWAC data collection window end | On track | DEC: Mid
2025/2026 | Software specification version 0.1 release | On track | FEB: Early
| Software supplier specification review period ends | On track | MAR: Mid
| Software specification version 1.0 release | On track | MAR: Late
| Schema, Summary, and Validation XSLT file set development by the Welsh Government | On track | MAY: Mid
| Schema, Summary, and Validation XSLT file set beta version (untested) release to suppliers | On track | JUN: Early
| Schema, Summary, and Validation XSLT file set version 1.0 (tested) release to suppliers | On track | JUL: Early
| Technical Completion Notes v1.0 release | On track | AUG: Late
| SWAC data collection window start | On track | NOV: Early
| SWAC data collection window end | On track | DEC: Mid
2026/2027 | Software specification version 0.1 release | On track | FEB: Early
| Software supplier specification review period ends | On track | MAR: Mid
| Software specification version 1.0 release | On track | MAR: Late
| Schema, Summary, and Validation XSLT file set development by the Welsh Government | On track | MAY: Mid
| Schema, Summary, and Validation XSLT file set beta version (untested) release to suppliers | On track | JUN: Early
| Schema, Summary, and Validation XSLT file set version 1.0 (tested) release to suppliers | On track | JUL: Early
| Technical Completion Notes v1.0 release | On track | AUG: Late
| SWAC data collection window start | On track | NOV: Early
| SWAC data collection window end | On track | DEC: Mid
2027/2028 | Software specification version 0.1 release | On track | FEB: Early
| Software supplier specification review period ends | On track | MAR: Mid
| Software specification version 1.0 release | On track | MAR: Late
| Schema, Summary, and Validation XSLT file set development by the Welsh Government | On track | MAY: Mid
| Schema, Summary, and Validation XSLT file set beta version (untested) release to suppliers | On track | JUN: Early
| Schema, Summary, and Validation XSLT file set version 1.0 (tested) release to suppliers | On track | JUL: Early
| Technical Completion Notes v1.0 release | On track | AUG: Late
| SWAC data collection window start | On track | NOV: Early
| SWAC data collection window end | On track | DEC: Mid

## EOTAS
Educated Otherwise Than At School (EOTAS)
Academic Year | Activity/Output | Status | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) | [16 empty] | NOTES
|  |  | JAN | FEB | MAR | APR | MAY | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN
2023/2024 | Software specification version 0.1 release | Delivered | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) MAY: Late; MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) AUG: Early | Late due to work related to sex data
| Software supplier specification review period ends | Delivered | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) JUL: Late; MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) SEP: Late | Late due to work related to sex data
| Software specification version 1.0 release | Delivered | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) JUL: Late; MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) SEP: Late | Late due to work related to sex data
| Schema, Summary, and Validation XSLT file set development by the Welsh Government | Delivered | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) JUL: Late; MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) SEP: Late | Late due to work related to sex data
| Schema, Summary, and Validation XSLT file set beta version (untested) release to suppliers | Late | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) AUG: Mid; MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) OCT: Mid | Late due to work related to sex data
| Schema, Summary, and Validation XSLT file set version 1.0 (tested) release to suppliers | Late | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) AUG: Late; MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) OCT: Late | Late due to work related to sex data
| Technical Completion Notes v1.0 release | Late | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) AUG: Late; MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) OCT: Early | Late due to work related to sex data
| EOTAS data collection window start | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) JAN: Mid
| EOTAS data collection window end | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) MAR: Early
2024/2025 | Software specification version 0.1 release | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) MAY: Late
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) JUL: Late
| Software specification version 1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) JUL: Late
| Schema, Summary, and Validation XSLT file set development by the Welsh Government | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) JUL: Late
| Schema, Summary, and Validation XSLT file set beta version (untested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) AUG: Mid
| Schema, Summary, and Validation XSLT file set version 1.0 (tested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) AUG: Late
| Technical Completion Notes v1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) AUG: Late
| EOTAS data collection window start | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) JAN: Mid
| EOTAS data collection window end | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) MAR: Early
2025/2026 | Software specification version 0.1 release | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) MAY: Late
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) JUL: Late
| Software specification version 1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) JUL: Late
| Schema, Summary, and Validation XSLT file set development by the Welsh Government | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) JUL: Late
| Schema, Summary, and Validation XSLT file set beta version (untested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) AUG: Mid
| Schema, Summary, and Validation XSLT file set version 1.0 (tested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) AUG: Late
| Technical Completion Notes v1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) AUG: Late
| EOTAS data collection window start | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) JAN: Mid
| EOTAS data collection window end | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) MAR: Early
2026/2027 | Software specification version 0.1 release | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) MAY: Late
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) JUL: Late
| Software specification version 1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) JUL: Late
| Schema, Summary, and Validation XSLT file set development by the Welsh Government | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) JUL: Late
| Schema, Summary, and Validation XSLT file set beta version (untested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) AUG: Mid
| Schema, Summary, and Validation XSLT file set version 1.0 (tested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) AUG: Late
| Technical Completion Notes v1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) AUG: Late
| EOTAS data collection window start | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) JAN: Mid
| EOTAS data collection window end | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) MAR: Early
2027/2028 | Software specification version 0.1 release | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) MAY: Late
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) JUL: Late
| Software specification version 1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) JUL: Late
| Schema, Summary, and Validation XSLT file set development by the Welsh Government | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) JUL: Late
| Schema, Summary, and Validation XSLT file set beta version (untested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) AUG: Mid
| Schema, Summary, and Validation XSLT file set version 1.0 (tested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) AUG: Late
| Technical Completion Notes v1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) AUG: Late
| EOTAS data collection window start | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) JAN: Mid
| EOTAS data collection window end | On track | MONTH NOTE: These months are for the year preceding and building up to the EOTAS data collection) MAR: Early

## PLASC
Pupil Level Annual School Census (PLASC)
Academic Year | Activity/Output | Status | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) | [16 empty] | NOTES
|  |  | JAN | FEB | MAR | APR | MAY | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN
2023/2024 | Software specification version 0.1 release | Delivered | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) MAY: Late; MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) AUG: Early | Late due to work related to sex data
| Software supplier specification review period ends | Delivered | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) JUL: Late; MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) SEP: Late | Late due to work related to sex data
| Software specification version 1.0 release | Delivered | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) JUL: Late; MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) SEP: Late | Late due to work related to sex data
| Schema, Summary, and Validation XSLT file set development by the Welsh Government | Delivered | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) JUL: Late; MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) SEP: Late | Late due to work related to sex data
| Schema, Summary, and Validation XSLT file set beta version (untested) release to suppliers | Late | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) AUG: Mid; MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) OCT: Mid | Late due to work related to sex data
| Schema, Summary, and Validation XSLT file set version 1.0 (tested) release to suppliers | Late | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) AUG: Late; MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) OCT: Late | Late due to work related to sex data
| Technical Completion Notes v1.0 release | Late | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) AUG: Late; MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) OCT: Early | Late due to work related to sex data
| PLASC data collection window start | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) JAN: Mid
| PLASC data collection window end | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) MAR: Early
2024/2025 | Software specification version 0.1 release | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) MAY: Late
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) JUL: Late
| Software specification version 1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) JUL: Late
| Schema, Summary, and Validation XSLT file set development by the Welsh Government | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) JUL: Late
| Schema, Summary, and Validation XSLT file set beta version (untested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) AUG: Mid
| Schema, Summary, and Validation XSLT file set version 1.0 (tested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) AUG: Late
| Technical Completion Notes v1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) AUG: Late
| PLASC data collection window start | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) JAN: Mid
| PLASC data collection window end | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) MAR: Early
2025/2026 | Software specification version 0.1 release | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) MAY: Late
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) JUL: Late
| Software specification version 1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) JUL: Late
| Schema, Summary, and Validation XSLT file set development by the Welsh Government | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) JUL: Late
| Schema, Summary, and Validation XSLT file set beta version (untested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) AUG: Mid
| Schema, Summary, and Validation XSLT file set version 1.0 (tested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) AUG: Late
| Technical Completion Notes v1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) AUG: Late
| PLASC data collection window start | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) JAN: Mid
| PLASC data collection window end | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) MAR: Early
2026/2027 | Software specification version 0.1 release | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) MAY: Late
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) JUL: Late
| Software specification version 1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) JUL: Late
| Schema, Summary, and Validation XSLT file set development by the Welsh Government | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) JUL: Late
| Schema, Summary, and Validation XSLT file set beta version (untested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) AUG: Mid
| Schema, Summary, and Validation XSLT file set version 1.0 (tested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) AUG: Late
| Technical Completion Notes v1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) AUG: Late
| PLASC data collection window start | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) JAN: Mid
| PLASC data collection window end | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) MAR: Early
2027/2028 | Software specification version 0.1 release | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) MAY: Late
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) JUL: Late
| Software specification version 1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) JUL: Late
| Schema, Summary, and Validation XSLT file set development by the Welsh Government | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) JUL: Late
| Schema, Summary, and Validation XSLT file set beta version (untested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) AUG: Mid
| Schema, Summary, and Validation XSLT file set version 1.0 (tested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) AUG: Late
| Technical Completion Notes v1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) AUG: Late
| PLASC data collection window start | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) JAN: Mid
| PLASC data collection window end | On track | MONTH NOTE: These months are for the year preceding and building up to the PLASC data collection) MAR: Early

## Attendance
Attendance (Primary and Secondary)
Academic Year | Activity/Output | Status | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) | [17 empty] | NOTES
|  |  | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
2023/2024 | Software specification version 0.1 release | Late | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) SEP: Late; MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) OCT: Mid | Late due to dependencies from previous developments
| Software supplier specification review period ends | Late | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) OCT: Late; MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) NOV: Early | Late due to dependencies from previous developments
| Software specification version 1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) NOV: Early
| Schema, Summary, and Validation XSLT file set development by the Welsh Government | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) NOV: Mid
| Schema, Summary, and Validation XSLT file set beta version (untested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) NOV: Late
| Schema, Summary, and Validation XSLT file set version 1.0 (tested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) DEC: Mid
| Technical Completion Notes v1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) FEB: Early
| Attendance: Secondary data collection window start | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) MAY: Late
| Attendance: Secondary data collection window end | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) JUL: Late
| Attendance: Primary data collection window start | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) JUL: Late
| Attendance: Primary data collection window end | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) SEP: Mid
2024/2025 | Software specification version 0.1 release | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) SEP: Late
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) OCT: Late
| Software specification version 1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) NOV: Early
| Schema, Summary, and Validation XSLT file set development by the Welsh Government | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) NOV: Early
| Schema, Summary, and Validation XSLT file set beta version (untested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) NOV: Late
| Schema, Summary, and Validation XSLT file set version 1.0 (tested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) DEC: Mid
| Technical Completion Notes v1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) FEB: Early
| Attendance: Secondary data collection window start | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) MAY: Late
| Attendance: Secondary data collection window end | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) JUL: Late
| Attendance: Primary data collection window start | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) JUL: Late
| Attendance: Primary data collection window end | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) SEP: Mid
2025/2026 | Software specification version 0.1 release | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) SEP: Late
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) OCT: Late
| Software specification version 1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) NOV: Early
| Schema, Summary, and Validation XSLT file set development by the Welsh Government | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) NOV: Early
| Schema, Summary, and Validation XSLT file set beta version (untested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) NOV: Late
| Schema, Summary, and Validation XSLT file set version 1.0 (tested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) DEC: Mid
| Technical Completion Notes v1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) FEB: Early
| Attendance: Secondary data collection window start | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) MAY: Late
| Attendance: Secondary data collection window end | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) JUL: Late
| Attendance: Primary data collection window start | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) JUL: Late
| Attendance: Primary data collection window end | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) SEP: Mid
2026/2027 | Software specification version 0.1 release | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) SEP: Late
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) OCT: Late
| Software specification version 1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) NOV: Early
| Schema, Summary, and Validation XSLT file set development by the Welsh Government | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) NOV: Early
| Schema, Summary, and Validation XSLT file set beta version (untested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) NOV: Late
| Schema, Summary, and Validation XSLT file set version 1.0 (tested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) DEC: Mid
| Technical Completion Notes v1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) FEB: Early
| Attendance: Secondary data collection window start | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) MAY: Late
| Attendance: Secondary data collection window end | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) JUL: Late
| Attendance: Primary data collection window start | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) JUL: Late
| Attendance: Primary data collection window end | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) SEP: Mid
2027/2028 | Software specification version 0.1 release | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) SEP: Late
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) OCT: Late
| Software specification version 1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) NOV: Early
| Schema, Summary, and Validation XSLT file set development by the Welsh Government | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) NOV: Early
| Schema, Summary, and Validation XSLT file set beta version (untested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) NOV: Late
| Schema, Summary, and Validation XSLT file set version 1.0 (tested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) DEC: Mid
| Technical Completion Notes v1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) FEB: Early
| Attendance: Secondary data collection window start | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) MAY: Late
| Attendance: Secondary data collection window end | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) JUL: Late
| Attendance: Primary data collection window start | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) JUL: Late
| Attendance: Primary data collection window end | On track | MONTH NOTE: These months are for the year preceding and building up to the Attendance data collections) SEP: Mid

## NDC
National Data Collection (NDC)
Academic Year | Activity/Output | Status | MONTH NOTE: These months are for the year preceding and building up to the NDC) | [17 empty] | NOTES
|  |  | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
2023/2024 | Software specification version 0.1 release | Late | MONTH NOTE: These months are for the year preceding and building up to the NDC) SEP: Late; MONTH NOTE: These months are for the year preceding and building up to the NDC) OCT: Mid | Late due to dependencies from previous developments
| Software supplier specification review period ends | Late | MONTH NOTE: These months are for the year preceding and building up to the NDC) OCT: Late; MONTH NOTE: These months are for the year preceding and building up to the NDC) NOV: Early | Late due to dependencies from previous developments
| Software specification version 1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) NOV: Early
| Schema, Summary, and Validation XSLT file set development by the Welsh Government | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) NOV: Mid
| Schema, Summary, and Validation XSLT file set beta version (untested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) NOV: Late
| Schema, Summary, and Validation XSLT file set version 1.0 (tested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) DEC: Mid
| Technical Completion Notes v1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) FEB: Early
| NDC data collection window start | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) MAY: Early
| NDC data collection window end | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) JUN: Early
2024/2025 | Software specification version 0.1 release | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) SEP: Late
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) OCT: Late
| Software specification version 1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) NOV: Early
| Schema, Summary, and Validation XSLT file set development by the Welsh Government | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) NOV: Mid
| Schema, Summary, and Validation XSLT file set beta version (untested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) NOV: Late
| Schema, Summary, and Validation XSLT file set version 1.0 (tested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) DEC: Mid
| Technical Completion Notes v1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) FEB: Early
| NDC data collection window start | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) MAY: Early
| NDC data collection window end | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) JUN: Early
2025/2026 | Software specification version 0.1 release | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) SEP: Late
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) OCT: Late
| Software specification version 1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) NOV: Early
| Schema, Summary, and Validation XSLT file set development by the Welsh Government | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) NOV: Mid
| Schema, Summary, and Validation XSLT file set beta version (untested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) NOV: Late
| Schema, Summary, and Validation XSLT file set version 1.0 (tested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) DEC: Mid
| Technical Completion Notes v1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) FEB: Early
| NDC data collection window start | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) MAY: Early
| NDC data collection window end | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) JUN: Early
2026/2027 | Software specification version 0.1 release | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) SEP: Late
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) OCT: Late
| Software specification version 1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) NOV: Early
| Schema, Summary, and Validation XSLT file set development by the Welsh Government | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) NOV: Mid
| Schema, Summary, and Validation XSLT file set beta version (untested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) NOV: Late
| Schema, Summary, and Validation XSLT file set version 1.0 (tested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) DEC: Mid
| Technical Completion Notes v1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) FEB: Early
| NDC data collection window start | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) MAY: Early
| NDC data collection window end | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) JUN: Early
2027/2028 | Software specification version 0.1 release | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) SEP: Late
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) OCT: Late
| Software specification version 1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) NOV: Early
| Schema, Summary, and Validation XSLT file set development by the Welsh Government | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) NOV: Mid
| Schema, Summary, and Validation XSLT file set beta version (untested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) NOV: Late
| Schema, Summary, and Validation XSLT file set version 1.0 (tested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) DEC: Mid
| Technical Completion Notes v1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) FEB: Early
| NDC data collection window start | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) MAY: Early
| NDC data collection window end | On track | MONTH NOTE: These months are for the year preceding and building up to the NDC) JUN: Early

## Post-16
Post-16
Academic Year | Activity/Output | Status | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) | [17 empty] | NOTES
|  |  | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
2023/2024 | Software specification version 0.1 release | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) FEB: Early
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) MAR: Early
| Software specification version 1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) MAR: Mid
| Schema, Summary, and Validation XSLT file set development by the Welsh Government | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) MAY: Mid
| Schema, Summary, and Validation XSLT file set beta version (untested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) JUN: Early
| Schema, Summary, and Validation XSLT file set version 1.0 (tested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) JUL: Early
| Technical Completion Notes v1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) JUL: Mid
| Post-16 data collection window start | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) SEP: Mid
| Post-16 data collection window end | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) OCT: Early
2024/2025 | Software specification version 0.1 release | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) FEB: Early
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) MAR: Early
| Software specification version 1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) MAR: Mid
| Schema, Summary, and Validation XSLT file set development by the Welsh Government | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) MAY: Mid
| Schema, Summary, and Validation XSLT file set beta version (untested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) JUN: Early
| Schema, Summary, and Validation XSLT file set version 1.0 (tested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) JUL: Early
| Technical Completion Notes v1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) JUL: Mid
| Post-16 data collection window start | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) SEP: Mid
| Post-16 data collection window end | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) OCT: Early
2025/2026 | Software specification version 0.1 release | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) FEB: Early
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) MAR: Early
| Software specification version 1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) MAR: Mid
| Schema, Summary, and Validation XSLT file set development by the Welsh Government | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) MAY: Mid
| Schema, Summary, and Validation XSLT file set beta version (untested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) JUN: Early
| Schema, Summary, and Validation XSLT file set version 1.0 (tested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) JUL: Early
| Technical Completion Notes v1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) JUL: Mid
| Post-16 data collection window start | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) SEP: Mid
| Post-16 data collection window end | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) OCT: Early
2026/2027 | Software specification version 0.1 release | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) FEB: Early
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) MAR: Early
| Software specification version 1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) MAR: Mid
| Schema, Summary, and Validation XSLT file set development by the Welsh Government | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) MAY: Mid
| Schema, Summary, and Validation XSLT file set beta version (untested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) JUN: Early
| Schema, Summary, and Validation XSLT file set version 1.0 (tested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) JUL: Early
| Technical Completion Notes v1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) JUL: Mid
| Post-16 data collection window start | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) SEP: Mid
| Post-16 data collection window end | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) OCT: Early
2027/2028 | Software specification version 0.1 release | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) FEB: Early
| Software supplier specification review period ends | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) MAR: Early
| Software specification version 1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) MAR: Mid
| Schema, Summary, and Validation XSLT file set development by the Welsh Government | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) MAY: Mid
| Schema, Summary, and Validation XSLT file set beta version (untested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) JUN: Early
| Schema, Summary, and Validation XSLT file set version 1.0 (tested) release to suppliers | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) JUL: Early
| Technical Completion Notes v1.0 release | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) JUL: Mid
| Post-16 data collection window start | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) SEP: Mid
| Post-16 data collection window end | On track | MONTH NOTE: These months are for the year preceding and building up to the Post-16 data collection) OCT: Early