## SDF 2018-19 Development Cycle
Task Name | Start | Finish | Resource
CTF18
Draft version 0.1 released |  | 2017-11-13 | DfE
Feed back to DfE on draft version if necessary | 2017-11-13 | 2017-12-08 | WG
Final version 1.0 released |  | 2018-02-23 | DfE
A_COMP 2018
Review modules and update as necessary | 2018-02-05 | 2018-06-27 | WG
Release v0.1 draft A_Comp |  | 2018-06-22
Develop January PLASC and EOTAS 2019
Specification | 2018-01-08 | 2018-02-12 | WG
Draft v0.1 specification release |  | 2018-02-12 | WG
Supplier review period | 2018-02-12 | 2018-03-12 | Suppliers
Version 1.0 specification release |  | 2018-04-23 | WG
Release validation CBDS |  | 2018-06-29 | WG
xslt development request | 2018-06-29 | 2018-07-27 | WG
DEWi development request | 2018-06-29 | 2018-07-27 | WG
xslt development | 2018-07-30 | 2018-08-10 | M4
DEWi developments | 2018-07-30 | 2018-08-10 | M4
Draft v0.1 xslt fileset released to suppliers |  | 2018-08-10 | WG
Supplier xslt review period | 2018-08-10 | 2018-08-24 | Suppliers
Undertake xslt and DEWi testing | 2018-08-20 | 2018-08-24 | WG
Compile final xslt fileset | 2018-08-27 | 2018-08-31 | M4
Final v1.0 fileset release |  | 2018-08-31 | WG
Release to supplier test DEWi sites |  | 2018-08-31 | M4/WG
Supplier version of completion notes released |  | 2018-08-31 | WG
Develop Attendance 2019
Specification | 2018-01-08 | 2018-02-12 | WG
Draft v0.1 specification release |  | 2018-02-12 | WG
Supplier review period | 2018-02-12 | 2018-03-12 | Suppliers
Version 1.0 specification release |  | 2018-05-11 | WG
Release validation CBDS |  | 2018-08-31 | WG
xslt development request | 2018-05-11 | 2018-08-31 | WG
DEWi development request | 2018-09-03 | 2018-10-19 | WG
xslt development | 2018-09-03 | 2018-09-24 | M4
DEWi developments | 2018-10-22 | 2018-12-03 | M4
Draft v0.1 xslt fileset released to suppliers |  | 2018-09-24 | WG
Supplier xslt review period | 2018-09-24 | 2018-10-12 | Suppliers
Undertake xslt testing | 2018-10-08 | 2018-10-12 | WG
Compile final xslt fileset | 2018-10-15 | 2018-10-19 | M4
Final v1.0 fileset release |  | 2018-10-19 | WG
Release to supplier test DEWi sites | 2018-10-29 | 2018-12-07 | M4/WG
Undertake DEWi testing | 2018-12-03 | 2018-12-07
Supplier version of completion notes released |  | 2018-12-14 | WG
Spring SDF meetings
Software Development Forum meeting* |  | 2018-02-22 | Suppliers/WG
CBDS (standard) change cycle
CBDS 18/19 published - Pupil/School |  | 2018-06-29 | WG
A_COMP published |  | 2018-06-22 | WG
QWAD, Programmes and Learning Providers look-ups published |  | 2018-06-29 | WG
WED 2018 on DEWi
DEWi development | 2018-08-06 | 2018-08-27 | M4/WG
DEWi UAT |  | 2018-08-02 | M4/WG
DEWi rework | 2018-08-27 | 2018-08-31 | M4/WG
Release to test DEWi site |  | 2018-08-31 | M4/WG
DEWi UAT on test site |  | 2018-09-07 | M4/WG
Release to live DEWi site |  | 2018-09-07 | M4/WG
Develop NDC 2019
Specification | 2018-05-07 | 2018-06-22 | WG
Draft v0.1 specification release |  | 2018-06-22 | WG
Supplier review period | 2018-06-22 | 2018-07-13 | Suppliers
Version 1.0 specification release |  | 2018-07-13 | WG
Release validation CBDS |  | 2018-08-31 | WG
xslt development | 2018-08-27 | 2018-09-24 | WG
Draft fileset release |  | 2018-09-24 | WG
Supplier review period | 2018-09-24 | 2018-10-15 | Suppliers
Final fileset release |  | 2018-10-15 | WG
DEWi developments | 2018-10-18 | 2018-12-03 | M4/WG
Release to supplier test DEWi sites | 2018-10-01 | 2018-12-03 | M4/WG
Supplier version of completion notes released |  | 2018-12-03 | WG
Develop WNT 2019
Specification |  | 2018-06-29 | WG
Draft specification release |  | 2018-06-29 | WG
Supplier review period | 2018-07-18 | 2018-08-02 | Suppliers
Version 1 specification release |  | 2018-08-02 | WG
Release validation CBDS |  | 2018-06-29 | WG
xslt development | 2018-06-29 | 2018-09-21 | WG
Draft fileset release |  | 2018-09-21 | WG
Supplier review period | 2018-09-21 | 2018-10-12 | Suppliers
Final fileset release |  | 2018-10-12 | WG
DEWi developments | 2018-10-15 | 2018-12-03 | M4/WG
Release to supplier test DEWi sites | 2018-10-29 | 2018-12-03 | M4/WG
Supplier version of completion notes released |  | 2018-12-03 | WG
Summer SDF meeting
Software Development Forum meeting |  | 2018-06-26 | Suppliers/WG
DEWI users
User audit | 2018-09-03 | 2018-09-28 | WG
Autumn SDF meetings
Software Development Forum meeting |  | 2018-10-23 | Suppliers/WG
Develop Post-16 October 2019
Specification | 2018-04-30 | 2018-06-15 | WG
Draft specification release |  | 2018-06-18 | WG
Supplier review period | 2018-06-18 | 2018-08-04 | Suppliers
Version 1 specification release |  | 2018-08-15 | WG
Release validation CBDS |  | 2018-09-01 | WG
xslt development | 2018-09-01 | 2018-09-22 | WG
Draft fileset release |  | 2018-09-22 | WG
Supplier review period | 2018-08-22 | 2018-10-13 | Suppliers
Final fileset release |  | 2018-10-13 | WG
DEWi developments | 2018-10-16 | 2018-12-01 | M4/WG
Release to supplier test DEWi sites | 2018-10-30 | 2018-12-01 | M4/WG
Supplier version of completion notes released |  | 2018-12-01 | WG
CTF19 consultation
Draft version 0.1 released |  | 2018-11-12 | DfE
Feed back to DfE on draft version if necessary | 2018-11-12 | 2018-12-07 | WG