## Sheet1
Task Name | Start | Finish | Resource | Updates
CTF17 draft release to suppliers |  | 2017-06-30 | DFE
A_COMP 2017 Review | 2017-02-01 | 2017-06-26 | WG
Develop January PLASC and EOTAS 2018
Specification | 2017-01-04 | 2017-02-02 | WG
Draft specification release |  | 2017-02-02 | WG
Supplier review period | 2017-02-02 | 2017-03-03 | Suppliers
Version 1 specification release |  | 2017-04-07 | WG
Release validation CBDS |  | 2017-07-07 | WG
xslt development | 2017-07-07 | 2017-07-28 | WG
Draft fileset release |  | 2017-07-28 | WG
Supplier review period | 2017-07-28 | 2017-08-18 | Suppliers
Final fileset release |  | 2017-08-25 | WG
DEWi developments | 2017-07-28 | 2017-09-29 | M4/WG
Release to supplier test DEWi sites |  | 2017-09-29 | M4/WG
Review and update the ULN collection, also taking into account of CTF changes |  | 2017-04-03 | WG
Supplier version of completion notes released |  | 2017-09-29 | WG
Develop Attendance 2018
Specification | 2017-01-04 | 2017-02-02 | WG
Draft specification release |  | 2017-02-02 | WG
Supplier review period | 2017-02-02 | 2017-03-03 | Suppliers
Version 1 specification release |  | 2017-06-29 | WG
Release validation CBDS |  | 2017-09-01 | WG
xslt development | 2017-09-01 | 2017-09-22 | WG
Draft fileset release |  | 2017-09-22 | WG
Supplier review period | 2017-09-22 | 2017-10-13 | Suppliers
Final fileset release |  | 2017-10-13 | WG
DEWi developments | 2017-10-16 | 2017-12-01 | M4/WG
Release to supplier test DEWi sites | 2017-10-30 | 2017-12-01 | M4/WG
Supplier version of completion notes released |  | 2017-12-01 | WG
Spring SDF meetings
Software Development Forum meeting* |  | 2017-02-02 | Suppliers
CTF17 final release to suppliers |  | 2017-07-07 | DFE
CBDS (standard) change cycle
CBDS 1718 published - Pupil/School |  | 2017-06-12 | WG
A_COMP published |  | 2016-06-26 | WG
Learning Activity, Programme of Study and Learning Provider look-ups published |  | 2017-06-28 | WG
WED 2017 on DEWi
DEWi development | 2017-07-03 | 2017-07-25 | M4/WG
DEWi UAT |  | 2017-07-25 | M4/WG
DEWi rework | 2017-07-28 | 2017-08-01 | M4/WG
Release to test DEWi site |  | 2017-08-01 | M4/WG
DEWi UAT on test site |  | 2017-08-08 | M4/WG
Release to live DEWi site |  | 2017-08-08 | M4/WG
Develop NDC 2018
Specification | 2017-05-03 | 2017-06-26 | WG
Draft specification release |  | 2017-06-26 | WG
Supplier review period | 2017-06-26 | 2017-08-02 | Suppliers
Version 1 specification release |  | 2017-08-03 | WG
Release validation CBDS |  | 2017-09-01 | WG
xslt development | 2017-09-01 | 2017-09-22 | WG
Draft fileset release |  | 2017-09-22 | WG
Supplier review period | 2017-09-22 | 2017-10-13 | Suppliers
Final fileset release |  | 2017-10-13 | WG
DEWi developments | 2017-10-16 | 2017-12-01 | M4/WG
Release to supplier test DEWi sites | 2017-10-30 | 2017-12-01 | M4/WG
Supplier version of completion notes released |  | 2017-12-01 | WG
Develop WNT 2018
Specification | 2017-05-03 | 2017-06-14 | WG
Draft specification release |  | 2017-06-14 | WG
Supplier review period | 2017-06-14 | 2017-08-04 | Suppliers
Version 1 specification release |  | 2017-08-07 | WG
Release validation CBDS |  | 2017-09-01 | WG
xslt development | 2017-09-01 | 2017-09-22 | WG
Draft fileset release |  | 2017-09-22 | WG
Supplier review period | 2017-09-22 | 2017-10-13 | Suppliers
Final fileset release |  | 2017-10-13 | WG
DEWi developments | 2017-10-16 | 2017-12-01 | M4/WG
Release to supplier test DEWi sites | 2017-10-30 | 2017-12-01 | M4/WG
Supplier version of completion notes released |  | 2017-12-01 | WG
Summer SDF meeting
Software Development Forum meeting |  | 2017-06-27 | Suppliers/WG
Software Development Forum meeting |  | 2017-07-12 | Suppliers/WG | Special workshop for School Workforce Collection
DEWI user audit | 2017-09-04 | 2017-09-29 | WG
Autumn SDF meetings
Software Development Forum meeting* |  | 2017-10-10 | Suppliers/WG
Software Development Forum meeting* |  | 2017-11-07 | Suppliers/WG
Develop Post-16 October 2018
Specification | 2017-04-07 | 2017-05-04 | WG
Draft specification release |  | 2017-05-04 | WG
Supplier review period | 2017-05-04 | 2017-08-04 | Suppliers
Version 1 specification release |  | 2017-08-15 | WG
Release validation CBDS |  | 2017-09-01 | WG
xslt development | 2017-09-01 | 2017-09-22 | WG
Draft fileset release |  | 2017-09-22 | WG
Supplier review period | 2017-09-22 | 2017-10-13 | Suppliers
Final fileset release |  | 2017-10-13 | WG
DEWi developments | 2017-10-16 | 2017-12-01 | M4/WG
Release to supplier test DEWi sites | 2017-10-30 | 2017-12-01 | M4/WG
Supplier version of completion notes released |  | 2017-12-01 | WG
CTF18 consultation | 2017-11-13 | 2017-12-08 | WG
*Potential to be cancelled