## Name List
Initials | Name | Organisation
AB | Alastair Birch | Welsh Government | This is the ist of initials and the individual matching them
ADA | Alice De'Abreu | Welsh Government | referred to within the actions log and the meeting minutes.
AI | Adam Irvine | Teacher Centre
AK | Andrew Kasper | Method 4 | Some may no longer be working in this area of work, but
AM | Andy Milne | Welsh Government | their initial may still appear on actions and minutes.
AMo | Alan Morris | Teacher Centre
AMs | Andy Miles | Selima Limited (Access UK Limited)
ARS | A R Shaw | RM
AT | Alison Tang | Welsh Government
BH | Beth Hurford | Zellis
BM | Beth Milton | Welsh Government
BW | Beverley Waltham | Capita
BWa | Bill Warnock | Capita
CC | Celia Coombs | Capita
CD | Ceri Davies | Cardiff Council
CH | Craig Hughes | Method 4
CHo | Claire Horton | Welsh Government
CM | Carol Mooney | Welsh Government
CO | Christopher Owen | Welsh Government
CPD | Carys Percy-Denning | Welsh Government
CRH | Chloe Harris | Welsh Government
CS | Cathy Silvey | City and County of Swansea Council
CW | Cerys Webber | Zellis
DAB | Don A'Bear | Welsh Government
DB | David Brown | Frontier Software
DG | Deborah Green | Capita ONE
DM | Dave Martland | Target Tracker
DNW | David Noel Williams | Gwynedd County Council
DP | Divya Padipura | Oracle
DR | David Rick | Capita
DW | Dan Wilkins | Tribal Group
GE | Gav Elias | Welsh Government
GEv | Glenn Evans | Carmarthenshire County Council
GH | Gerard Hassett | Department for Education
GP | Gareth Pritchard | Vale of Glamorgan Council
GRC | Gemma Roche-Clarke | Welsh Government
GS | Graham Simpson | Frontier Software
GT | Gareth Thomas | Welsh Government
GW | Glyn Walley | Denbighshire County Council
HC | Helen Clark | OLM Systems
IRS | Ian Romeo-Smith | Capita
JB | James Boyd | Cardiff Council
JBa | Jane Barnard | Capita
JDi | James Dix | Welsh Government
JD | Justin Denney | Teacher Centre
JE | Jes East | Capita
JG | James Gilbert | Welsh Government
JGi | Jane Gibson | Selima Limited (Access UK Limited)
JH | Jim Haywood | Capita SIMS
JHo | James Hornby | Method 4
JL | Jon Leyshon | Department for Education
JT | Jayne Thomas | Neath Port Talbot County Borough Council
JTr | John Tratnik | Rhondda Cynon Taf County Borough Council
JV | Jo Valentine | Welsh Government
KC | Katherine Cameron | Frontier Software
KK | Kirsty Knox | Department for Education
KM | Kieran Mitchell | Method 4
KN | Khurshid Nahami | Capita
LH | Luke Howells | Carmarthenshire County Council
LL | Lindsay Lewis | Welsh Government
LP | Like Pibworth | Capita ONE
LR | Lucy Robinson | Welsh Government
LS | Lee Sapsford | Capita
LW | L Walsh | Caci
MBa | Martin Baker | Bromcom Computer Plc
MB | Melanie Brown | Welsh Government
MC | Meg Colley | Welsh Government
MCu | Marilyn Curtis | Capita
MJ | Mike Jones | City and County of Swansea Council
MM | Mike Maher | Welsh Government
MMa | Manon Maragakis | Welsh Government
MS | Michael Stewart | ESP Thinking
MT | Mark Thomas | Carmarthenshire County Council
MTh | Mark Thornhill | Selima Limited (Access UK Limited)
MW | Mark Weaver | Cardiff Council
MWh | Michael White | Zellis
MWa | Matt Walker | RM
MWF | Mei Wah Farrow | Cardiff Council
NB | Narinder Bansal | Digitech Software
ND | Nicola Dicks | Capita
NF | Nicholas Finnemore | Finnemore Consulting
NG | Nicola Giles | Welsh Government
NGh | Neha Ghawalkar | Capita ONE
NM | Neil Morris | Pembrokeshire County Council
NT | Neil Tonks | MHR
NY | Niranjan Yedamakanti | Capita ONE
PB | Paul Bates | Capita
PBu | Peter Burns | Zellis
PD | Phil Dent | Department for Education
PDJ | Phil D Jones | Capita
PF | Paul Featherstone | Capita
PG | Paul Grubb | Selima Limited (Access UK Limited)
PH | Peter Henderson | Pisys
PJ | Philipa Jones | Carmarthenshire County Council
PL | Peter Lambe | MHR
PM | Paul Moyle | Welsh Government
PP | Peter Phillips | Capita
PW | Paul Walton | Capita SIMS
RC | Rodel Currie | Cardiff Council
RH | Rhodri Huws | Welsh Government
RL | Rachel Lloyd | Welsh Government
RM | Rachael Marshman | Capita
RMa | Rozina Majid | Capita
RRF | Rhian Rickard-Frost | Cardiff Council
RS | Rachel Shepherd | Welsh Government
RT | Rachel Thomas | Welsh Government
RV | Ruth Vincent | Capita SIMS
SA | Sarah Angel | Welsh Government
SC | Sarah Chandler | Go4Schools
SE | S Evans | Cardiff Council
SH | Steve Hughes | Welsh Government
SHe | Sara Herbert | Vale of Glamorgan Council
SI | Sarah Irvine | Teacher Centre
SL | Simon Lewis | Bromcom Computer Plc
SP | Simon Pike | Capita
SR | Suky Rana | Capita
SRo | Sue Rountree | Sum Total Systems
SS | Simon Smith | Capita
SW | Sophie Williams | Oracle
TJ | T Jones | Carmarthenshire County Council
TJo | Tom Jones | Capita
TO | Tom Osborne | Capita ONE
TS | Tim Snell | Welsh Government
TSe | T Selby | RM
VB | Vikki Blakemore | MHR
YD | Yvonne Davies | Flintshire County Council
YK | Yvonne Killick | Capita

## All Open Actions
Ref | Date Raised | Agenda Item | Action | Owner | Status | Target completion or completed date | Update
SDF-402 | 2019-06-04 | SWAC | Capita to confirm when the delete teacher function will be available to local authorities. | Capita | Open |  | This action is still on going, request update for November meeting.
SDF-411 | 2019-07-04 | Performance Reporting | The Welsh Government, suppliers and local authorities to agree dates to extract data from QiW to ensure harmonisation. | WG (SA) | Open
SDF-413 | 2019-10-17 | Performance Reporting | QiW extracts. PW to provide SA with examples of extracts not reflecting accurate data. | Capita/WG (PW/SA) | Open
SDF-414 | 2019-10-17 | Performance Reporting | SSSP with issues in requests coming in that converted to Excel | WG (SH) | Open
SDF-418 | 2019-10-17 | MISC | DG to liaise with RCT on portal technology | Capita (DG) | Open
SDF-422 | 2020-02-06 | Performance Reporting | SH to share extract schedule with minutes of the meeting | WG (SH) | Open
SDF-423 | 2020-02-06 | Performance Reporting | SH to seek to clarify documentation where needed. | WG (SH) | Open
SDF-424 | 2020-02-06 | Performance Reporting | SH to discuss with colleagues whether it is possible to provide a Microsoft Excel format file as well as an XML. | WG (SH) | Open
SDF-427 | 2020-02-06 | ALN | SIIB to set up workshops with policy and software suppliers to look at technical solution once policy have had internal agreements and clearances necessary. | WG (GE) | Open
SDF-428 | 2020-03-05 | SWAC | WG to provide a summary of outstanding issues and errors triggered when running the cross-validations to LAs | WG (GT) | Open
SDF-429 | 2020-03-05 | SWAC | WG to produce a brief summary guide for schools on completing SWAC | WG (GT) | Open
SDF-430 | 2020-03-05 | SWAC | WG to include ethnicity on agenda for next SDF meeting | WG (GT) | Open
SDF-431 | 2020-03-05 | SWAC | Add FTE against main roles in SWAC 2020 | WG (GT) | Open
SDF-432 | 2020-03-05 | SWAC | Add Status data item in SWAC 2020 | WG (GT) | Open
SDF-433 | 2020-03-05 | SWAC | Add ‘ThirdParty’ data item against workforce member in SWAC 2020 | WG (GT) | Open
SDF-434 | 2020-03-05 | SWAC | Expand on guidance for recording cover supervisors and consider re-naming code description to ‘Cover Manager’ | WG (GT) | Open
SDF-435 | 2020-03-05 | SWAC | Produce detailed guidance on how schools should record supply data | WG (GT) | Open
SDF-437 | 2020-03-05 | P16 | The Welsh Government to explore Post-16 activities that are coming in with a completion of over 100% and how this could be rectified | WG (GE) | Open

## All On Hold Actions
Ref | Date Raised | Agenda Item | Action | Owner | Status | Target completion or completed date | Update
SDF-267 | 2016-10-11 | AOB | WG to provide an update on the Early Years census | WG | On hold |  | This is currently on hold.
SDF-358 | 2018-06-26 | AOB | SIIB to continue discussions with DfE/LRS on this issue to establish what is possible on obtaining ULNs earlier, both in a technical and data protection capacity. | WG (GE) | On hold |  | This is currently on hold whilst exploring ICO advice given to LRS and the recent LRS data breach.
SDF-366 | 2019-02-07 | Attendance | AP will confirm definition when drafting new codes | WG (KM/BP) | On hold |  | Policy development is under way and on hold until future meetings
SDF-367 | 2019-02-07 | Attendance | AP to check with KAS colleagues and get clarity on the use of codes as discussed. | WG (KM/BP) | On hold |  | Policy development is under way and on hold until future meetings
SDF-368 | 2019-02-07 | Attendance | Definition of part time hours also needed | WG (KM/BP) | On hold |  | Policy development is under way and on hold until future meetings
SDF-369 | 2019-02-07 | Attendance | AP to consider the use of B and D codes | WG (KM/BP) | On hold |  | Policy development is under way and on hold until future meetings
SDF-394 | 2019-04-26 | PLASC | The Welsh Government to consider whether schools can resolve queries rather than relying on local authorities. | WG (GE) | On hold |  | This is currently on hold whilst Welsh Government are exploring future developments for DEWi and how this could be accommodated
SDF-393 | 2019-04-26 | PLASC/Attendance | The Welsh Government to consider whether it is feasible to move exclusions data from PLASC into attendance collection | WG (GE) | On hold |  | This will require thorough consideration and this is currently being done. The action is on hold until this exploration has been done.
SDF-421 | 2019-10-17 | EHE | CM to arrange a breakout session to discuss EHE proposals further | WG (CM/AB) | On hold

## All Closed Actions
Ref | Date Raised | Agenda item | Action | Owner | Status | Target completion or completed date | Update
68 | 2013-07-01 | Any Other Business | Provide PLASC data to Cardiff and Swansea to investigate discrepancies on the calculation of fixed-term exclusions | WG - SHu/MS | 2014-07-01 | NA | Three local authorities were sent their data to compare in July, but we have still not heard back from them 10/11/14.
92 | 2014-02-11 | Post-16 | Provide a mapping table for Activities to Programmes | WG - AO | 2014-06-04 |  | Duplication of actions 118 and 119.
96 | 2014-02-11 | Response Times | Revised approach to response times to be reviewed in 3 months | WG - CHo | 2014-06-04 |  | Reviewed at SDF meeting on 04/06/14 and agreed that there has been an improvement and that the action could be re-opened if necessary in future.
97 | 2014-02-11 | Response Times | Investigate the use the of issues log within DEWi for supplier queries | WG - CHo | 2014-06-04 |  | Can be re-opened in future if deemed necessary, see action 96.
100 | 2014-03-18 | Jan. PLASC 2015 Amended Specification | Review School Governance in PLASC after PLASC 2015 | WG - CHo | 2016-02-01 |  | To be reviewed for 2017 spec, due in February 2016. No change to school federations in PLASC
104 | 2014-03-18 | Jan. PLASC 2015 Amended Specification | Arrange a review of summary reports | WG - CHo | 2016-10-11 |  | Working group arranged for 15 November 2016 SDF
105 | 2014-03-18 | EOTAS 2015 Amended Specification | Provide information on EOTAS funding and the prevention of double counting between main and EOTAS provisions | WG - SHu | 2014-06-04 |  | SH confirmed that there are a number of checks in place to prevent double counting at the SDF meeting on 04/06/14.
108 | 2014-03-18 | EOTAS 2015 Amended Specification | Provide guidance on SEN rankings in PLASC and EOTAS | WG - CHo | 2014-06-04 |  | CHo confirmed that this will be included in guidance for PLASC & EOTAS 2015 at the SDF meeting on 04/06/14.
110 | 2014-03-18 | NDC and National Tests | WG confirm file formats for NDC file downloads from DEWi | WG - CHo | 10/02/2015 See ref 164 |  | CHo requested more information on this at the SDF meeting on 04/06/14 and will now work with suppliers to ensure LAs are able to import tests data for 2015
112 | 2014-03-18 | Post-16 2015 Draft Specification | WG inform schools of the post-16 changes | WG - AO | 2014-11-11 |  | AO confirmed at SDF on 11 November that meetings have been held with schools and the completion notes will cover any changes.
114 | 2014-03-18 | Post-16 2015 Draft Specification | Post-16 Technical Completion Notes to be made available to suppliers/ uploaded to DEWi SDF | WG - AO | 2014-07-01 |  | Completion notes for 2014 released to SDF site
115 | 2014-03-18 | Post-16 2015 Draft Specification | New summary reports should include blank/zero lines | WG - AO | 2014-06-04 |  | AO advised that this would not be feasible at the SDF meeting on 04/06/14.
116 | 2014-03-18 | Post-16 2015 Draft Specification | Post-16 Technical Completion Notes to state which pupils should be included in the return | WG - AO | 2014-07-01 |  | Included in completion notes
117 | 2014-03-18 | Post-16 2015 Draft Specification | WG to provide guidance on mature learners, the P-16 collection and UPNs | WG | 2015-01-05 |  | Included in completion notes for 2015
118 | 2014-03-18 | Post-16 2015 Draft Specification | WG to provide mapping table to the SDF and LA Data/IMS teams | WG - AO | 2014-06-04 |  | AO advised that this would not be feasible at the SDF meeting on 04/06/14.
119 | 2014-03-18 | Post-16 2015 Draft Specification | A link to the mapping table to be included in Post-16 Completion Notes | WG - AO | 2014-06-04 |  | As action 118.
120 | 2014-03-18 | XSLT fileset naming convention | WG to review fileset numbering | WG - CHo | 2014-06-04 |  | Discussed at the SDF meeting on 04/06/14 and agreed to trial new fileset release note with January 2015 xslt files.
121 | 2014-03-18 | A.O.B. | WG to research the issue of commas within pupil names | WG - CHo | 2015-05-19 |  | CHo requested more information on this at the SDF meeting on 04/06/14 and will now work with Method4 to ensure the issue can be resolved.
122 | 2014-06-04 | Minutes, actions and matters arising from the meeting on 18 March 2014 | WG to amend procedures to ensure that guidance notes for all collections are made available as early as possible on the SDF site. | WG | 2014-11-01 |  | Implemented for Post-16
123 | 2014-06-04 | EYDAF and Curriculum Review | WG to consider impact of EYDAF on CTF. | WG |  |  | CTF paper for FPP in progress
124 | 2014-06-04 | NDC & National Tests 2015 | Suppliers to confirm that this change can be implemented. | Suppliers | 2014-12-19 |  | Confirmation from Advanced Learning and Capita received - 10/11/2014 RM - 19/12/2014
125 | 2014-06-04 | NDC & National Tests 2015 | CHo to add the import file structure to the specification and publish on the SDF site. | WG - CHo | 2014-06-13 |  | Released to SDF site
126 | 2014-06-04 | NDC & National Tests 2015 | CHo to ensure that historical components are retained in the Excel versions of A_COMP and that only the current year's components are included in the specification. | WG - CHo | 2014-06-13 |  | Released to SDF site
127 | 2014-06-04 | NDC & National Tests 2015 | WG to provide 2013 test data to LAs. | WG | 2015-01-13
128 | 2014-06-04 | NDC & National Tests 2015 | WG to provide clear communications on the revision of 2013 reading test scores. | WG | 2015-02-10 |  | Email sent 19/01/2015
129 | 2014-06-04 | NDC & National Tests 2015 | WG to work with suppliers to ensure revised scores are delivered to schools as soon as possible with clear instructions. | WG | 2015-07-22 |  | Provided to LAs but without an automated process. Incorrect data successfully deleted from all systems.
130 | 2014-06-04 | NDC & National Tests 2015 | SH to distribute revised quartiles. | WG - SH |  |  | Issued for 2015
131 | 2014-06-04 | NDC & National Tests 2015 | WG to respond to Mike's query. [language of test] | WG | 2014-06-06 |  | KAS confirmed data to be submitted for this pupil.
132 | 2014-06-04 | NDC & National Tests 2015 | CHo to confirm xsd filesets for summer 2015. | WG - CHo | 2014-06-10 |  | Confirmed by email.
133 | 2014-06-04 | Post-16 2015 | AO to include line in specification that software does not have to validate activities within programmes. | WG - AO | 2014-07-15 |  | Included in Post-16 spec (Version 2.0)
134 | 2014-06-04 | Post-16 2015 | AO to provide LAs information on the changes to the post-16 collection. | WG - AO | 2014-06-12 |  | Email from Sian James to LAs
135 | 2014-06-04 | Post-16 2015 | WG to consider validation rules. | WG - SJ | 2014-08-04 |  | Validation CBDS v1516.0.0 released to SDF site, including validation rules for some programmes.
136 | 2014-06-04 | Post-16 2015 | WG to clarify in the specification if subjects are being recorded but not used for performance. | WG - AO | 2014-07-15 |  | Policy team confirmed that data on all activities from 01/09 each year are to be included in the return
137 | 2014-06-04 | Post-16 2016 | Suppliers to notify schools not to change the year taught data item until September. | Suppliers | 2014-12-19 |  | Confirmation from Advanced Learning and Capita received.
138 | 2014-06-04 | 2014 Performance Tables | SH to share stakeholder survey results with SDF. | WG - SH | 2014-11-10 |  | Link to stakeholder survey sent to SDF mailing list.
139 | 2014-06-04 | 2014 Performance Tables | SH to share the discounting table for Wales. | WG - SH | 2015-05-29 |  | 19/11/2014 - We will share the latest (2014) list with suppliers as soon as the 2014 exercise is closed. Published on 29/05/2015, 2015 and 2016 list will be the same as 2014.
140 | 2014-06-04 | 2014 Performance Tables | SH to review the outcome and advise SDF of any implications for summary reports that suppliers may provide in their systems. | WG - SH |  |  | 19/11/2014 - impact of survey results will happen in 2016
141 | 2014-06-04 | EOTAS 2016 | WG to consider the double counting issue when including exclusions in the EOTAS 2016 draft specification. | WG - CHo | 2015-01-27 |  | Spec sent with papers for 10/02/2015 SDF meeting
142 | 2014-06-04 | XSLT fileset naming convention | WG to trial release note with next release of new xslt filesets. | WG |  |  | Completed for Jan 2015 XSLT
143 | 2014-06-04 | SDF Cycle | CHo to send out more information on the changes. | WG - CHo | 2014-06-09 |  | Email with details of the change sent to SDF
144 | 2014-06-04 | AOB | WG to contact LAs for feedback on this item. [penalty notices] | WG - CHo | 2014-12-15 |  | Email sent to LA's circulated to SDF contacts 15/12/2014
145 | 2014-06-04 | AOB | CHo to get in touch with LH to resolve the query. [action 103, exceptions] | WG - CHo | 2014-06-05 |  | Query passed to policy team for response
146 | 2014-06-04 | AOB | CHo to get in touch with LH to resolve the query. [ULN] | WG - CHo | 2014-06-18 |  | Resolved between WG, RM, LA and school
147 | 2014-11-11 | Minutes, actions and matters arising from the meeting on 4 June, 2014 | WG to amend Post-16 guidance notes to include year taught definition | WG -SJ | 2015-01-27 |  | To be discussed at SDF
148 | 2014-11-11 | Post-16 2016 | AO to clarify what key skills data is needed from schools. | WG - AO | 2015-01-09 |  | Clarification added to completion notes (Section 6)
149 | 2014-11-11 | Post-16 2016 | Spec to be updated to show which look-ups go with which collection. | WG - SJ | 2015-01-26 |  | Revised spec sent
150 | 2014-11-11 | Post-16 2016 | WG to amend spec to state suppliers are to make it easier to add providers. | WG - SJ | 2015-04-29 |  | Spec to be updated in next version 27/01/2015
151 | 2014-11-11 | Post-16 2014 | AO to confirm how duplicate learning activities should be dealt with (school timetabling). | WG - AO | 2015-01-26 |  | Revised spec sent
152 | 2014-11-11 | Post-16 2014 | SJ to update Spec and completion notes with a definition of a learning activity. | WG - SJ | 2015-02-10 |  | Spec updated 26/01/2015, completion notes to be published
153 | 2014-11-11 | Post-16 2014 | AO to confirm if Welsh schools can choose to deliver the two-year A-levels and to check funding arrangements for these courses. | WG - AO | 2015-02-10 |  | Policy confirmed two year A Levels not available in Wales
154 | 2014-11-11 | Post-16 2014 | WG to follow up on new attendance guidance and ensure it covers dual registration. | WG |  |  | New attendance guidance is being consulted on in early 2015.
155 | 2014-11-11 | Issues arising during the collection | Suppliers to update points of contact. | Suppliers | 2015-02-10 |  | All suppliers updated points of contact
156 | 2014-11-11 | National Tests Update | CHo to get consensus across all LAs for the best format for import files in 2015. | WG - CHo | 2015-06-02 |  | Partial CTF format agreed by all suppliers 02/06/2015
157 | 2014-11-11 | National Tests Update | Suppliers to consider the deletion of 2013 data and feedback on any issues. | Suppliers | 2015-02-10 |  | Email sent to SDF group 19/01/15
158 | 2014-11-11 | National Tests Update | CHo to provide clear guidance on how <, >, X and D scores are to be included when aggregating results. | WG - CHo | 2015-01-26 |  | Email sent to LAs 26/01/15
159 | 2015-02-10 | Foundation Phase Profile and Curriculum Review | WG to circulate the Foundation Phase Profile User Guide when available. | WG - CS |  |  | Uploaded to DEWi - 20/02/2015
160 | 2015-02-10 | Foundation Phase Profile and Curriculum Review | WG to consider children who cannot achieve a skill, e.g. disapplication when creating the skill ladders | WG - CS | 2015-05-19 |  | 15/04/15 - Disapplication taken into account in draft A_Comp. Reviewing the results of the trial from Special Schools, no issues raised. Will be discussed 02/06/2015
161 | 2015-02-10 | Foundation Phase Profile and Curriculum Review | WG to request information from DfE about reporting from 0 years of age. | WG - CHo | 2015-02-10 |  | Part of CS research
162 | 2015-02-10 | Foundation Phase Profile and Curriculum Review | WG to arrange a meeting with suppliers after the pilot and before August to discuss reporting | WG - CS | 2015-05-19 |  | Near final draft will be available from the 14 May (will be proof reading at this point). We will therefore be able to confirm ladders and which outcomes have statements. FPP will be signed off by Minister on 3 June, happy to circulate following this. Meeting to replace June SDF.
163 | 2015-02-10 | Foundation Phase Profile and Curriculum Review | WG to complete a draft specification and A_Comp by the next meeting, 10 March. | WG - JA | 2015-05-22 |  | 06/3/15 - Draft A - COMP added to DEWi, V0.1 22/05/15 - Draft Spec added to DEWi, V0.1
164 | 2015-02-10 | NDC & National Test Update | WG to circulate the CSV specification | WG - CHo | 2015-05-19 |  | Uploaded to DEWi
165 | 2015-02-10 | NDC & National Test Update | WG to keep suppliers informed on actions for import files. | WG - CHo | 2015-07-22
166 | 2015-02-10 | NDC & National Test Update | WG to circulate correspondence with instructions for deleting the data. | WG - CHo | 2015-07-22 |  | Incorrect data successfully deleted from all systems.
167 | 2015-02-10 | Interventions Monitoring | WG to consider the role of the LA, data collection and CTF for monitoring interventions. | WG | 2016-10-11 |  | Closed with agreement to revisit once this work is recommenced
168 | 2015-02-10 | Interventions Monitoring | WG to consider defining data for CBDS. | WG | 2016-10-11 |  | Closed with agreement to revisit once this work is recommenced
169 | 2015-02-10 | Interventions Monitoring | WG to circulate key dates of the Interventions Monitoring programme | WG | 2016-10-11 |  | Closed with agreement to revisit once this work is recommenced
170 | 2015-02-10 | Post-16 2016 | WG to confirm release dates for look up tables | WG - SJ | 2015-05-29 |  | Email sent with release dates
171 | 2015-02-10 | Post-16 2016 | WG to amend on roll date description to include ‘during previous academic year’. | WG - SJ | 2015-04-29 |  | 2015 and 2016 Specifications released
172 | 2015-02-10 | Post-16 2016 | WG to add detail to the specification for the point in time that NCYear should be taken. | WG - SJ | 2015-04-29 |  | 2015 and 2016 Specifications released
173 | 2015-02-10 | Post-16 2016 | LAs to find out if it is recorded if pupils start early. | LAs | 2016-06-01 |  | Agreed to be closed in 1st June 2016 meeting
173 | 2015-02-10 | Post-16 2016 | LAs to find out if it is recorded if pupils start early. | LAs |  |  | Agreed to be closed in 1st June 2016 meeting
174 | 2015-02-10 | Post-16 2016 | WG to send guidance on the Post 16 collection to LAs | WG - NHO | 2015-06-16
175 | 2015-02-10 | Post-16 2016 | WG to confirm with suppliers how the XSLT will differentiate between Post-16 2015 and 2016. | WG - SJ | 2015-05-29 |  | Email sent with differentiations
176 | 2015-02-10 | WG to amend information on duplicate learning activities. |  | WG - SJ | 2015-04-29 |  | Updated Specification released
177 | 2015-02-10 | PLASC spec 2016 | Suppliers to review and agree the PLASC specification by the next meeting, scheduled for 10 March 2015. | Suppliers | 2015-03-05 |  | Specification reviewed and agreed
178 | 2015-02-10 | Attendance spec 2016 | Suppliers to review and agree the Attendance specification by the next meeting, scheduled for 10 March 2015. | Suppliers | 2015-03-05 |  | Specification reviewed and agreed
179 | 2015-02-10 | EOTAS spec 2016 | Suppliers to review and agree the EOTAS specification by next meeting, scheduled for 10 March 2015. | Suppliers | 2015-03-05 |  | Specification reviewed and agreed
180 | 2015-02-10 | AOB | WG to circulate 2015/16 SDF cycle | WG - CHo | 2015-05-19 |  | Uploaded to DEWi - 19/05/2015
181 | 2015-02-10 | AOB | WG to consider the timing of CTF versioning and ensure that LRS is using the right version for ULN files. | WG - CHo | 2015-05-19 |  | Included in Jan PLASC development request
182 | 2015-06-02 | Minutes, actions and matters arising from the meeting on 10 February 2015 | Suppliers to confirm how the new discount codes have been integrated. | Suppliers | 2015-11-17 |  | Closed and re-opened as Action 203
183 | 2015-06-02 | Minutes, actions and matters arising from the meeting on 10 February 2015 | WG to add Validation CBDS to the 2015/16 SDF cycle. | WG - CH | 2015-09-17
184 | 2015-06-02 | Minutes, actions and matters arising from the meeting on 10 February 2015 | WG to send out PLASC Validation CBDS. | WG - CH | 2015-07-03
185 | 2015-06-02 | Foundation Phase Profile | WG to consider how the baseline assessment of children entering a setting after the NDC in May will be recorded for 2016/17 onwards. | WG - CS | 2015-07-13 |  | Agreement that any pupils entering a setting after the NDC in May will not be recorded in 2016
186 | 2015-06-02 | Foundation Phase Profile | WG to update the Specification to reflect the Handbook’s definition of ‘reception’. | WG - AS | 2015-07-13 |  | Spec only now refers to NCY R (and next year it will refer to NCY R and NCY 1, when revised outcome statements are valid for NCY 1).
187 | 2015-06-02 | Foundation Phase Profile | WG to clarify whether pupils joining from another education system have to have a baseline assessment. | WG - CS | 2015-07-13 |  | Only the first baseline assessment is considered statutory and should be returned to WG, schools may choose to re assess but this is not considered statutory
188 | 2015-06-02 | Foundation Phase Profile | WG to review the requirement for ‘result date’ and consult with SDF. | WG - CS | 2015-07-13 |  | New data item <dateofcompletion> added to the schema
189 | 2015-06-02 | Foundation Phase Profile | WG to consider creating a temporary solution for recording the baseline assessment for data collection in September 2015. | WG - CS | 2015-07-13 |  | Spreadsheet for schools to record baseline assessments sent to SDF for consideration on 04/09/2015
190 | 2015-06-02 | Foundation Phase Profile | WG to release final A_Comp. | WG - AS | 2015-07-13
191 | 2015-06-02 | NDC Draft Specification 2016 | WG to use a different colour to identify changes from the previous version of the May 2016 specification and to explain the colour coding. | WG - AS | 2015-07-13 |  | Green used to highlight changes from the last version in specification and A_Comp.
192 | 2015-06-02 | NDC Draft Specification 2016 | WG to consider the transfer of FPP data and to indicate in A_Comp, or elsewhere, if possible, which data schools may want to transfer via CTF (in advance of the CTF specification being available). | WG - AS | 2016-02-02 |  | Closed as incorporated into action 230
193 | 2015-06-02 | NDC Draft Specification 2016 | WG to clarify in 2.1.2 that the end of FP assessment remains unchanged. | WG - AS |  |  | Version 3.0 of the spec released 23/10/15
194 | 2015-06-02 | NDC Draft Specification 2016 | WG to be explicit in A_Comp, for the avoidance of doubt, about which fields should have a value or be null. | WG - AS |  |  | Version 2.0 of A_COMP released 23/10/15
195 | 2015-06-02 | NDC Draft Specification 2016 | WG to update the Specification to identify that the FEWBES item in the KS4/KS5 container only relates to KS4. | WG - AS | 2015-07-13 |  | Spec clarifies that it relates to KS4 pupils only.
196 | 2015-06-02 | NDC Draft Specification 2016 | WG to consider whether NCyear 11 and/or aged 15 are both required and amend specification if necessary. | WG - AS | 2015-09-17 |  | Confirmed that NCyear 11 and/or aged 15 are both still required for NDC 15/16.
197 | 2015-06-02 | NDC Draft Specification 2016 | WG to provide a spreadsheet with a full list of ladders separately to the A_Comp and handbook. | WG - CS | 2015-07-13 |  | Issued on 13/07/2015
198 | 2015-06-02 | NDC Draft Specification 2016 | WG to circulate the handbook and presentation to suppliers. | WG - CS | 2015-07-13 |  | Issued on 13/07/2015
199 | 2015-06-02 | AOB | SDF cycle to flag any meetings that may be cancelled. | WG - RE | 2015-09-17
200 | 2015-06-02 | AOB | WG to advise whether the pupil count will use January or May data for KS4 reporting. | WG - KAS | 2015-11-17 |  | Closed and replaced with 202
201 | 2015-06-02 | AOB | WG to electronically circulate the document “Measuring secondary school performance in Wales”. | WG - RE | 2015-09-17
202 | 2015-11-17 | Minutes, actions and matters arising from the meeting on 2 June 2015 | WG to confirm in writing the decisions regarding the collection of KS4 cohort data. | WG | 2016-02-02 |  | SH provided this at the SDF meeting and a link to the letter published online can be found in the minutes.
203 | 2015-11-17 | Minutes, actions and matters arising from the meeting on 2 June 2015 | Suppliers to confirm how the new discount codes have been integrated, in response to forthcoming email from CH. | Suppliers | 2016-02-02 |  | Closed as duplicated action 228
204 | 2015-11-17 | Foundation Phase Profile (FPP) update | AS to consider downgrading validation errors to queries that trigger for pupils in NCY1 who legitimately have no BA results. | WG - AS | 2016-03-01 |  | These will remain as errors.
205 | 2015-11-17 | Foundation Phase Profile (FPP) update | WG to identify scenarios and guidance for ‘non-standard’ pupils for the NDC-BA collection. | WG - AS | 2016-02-01 |  | Policy FAQs provide advice.
206 | 2015-11-17 | Foundation Phase Profile (FPP) update | AS to consider a BA report to help with validation. | WG - AS | 2016-05-10 |  | Done.
207 | 2015-11-17 | Foundation Phase Profile (FPP) update | AS to consider providing guidance to schools about: 1. NCY1 pupils who legitimately have no BA results and who trigger errors/queries in validation. 2. DOB ranges for pupils who should be included in the NDC-BA file. | WG - AS | 2016-05-21 |  | Guidance released 21.04.16
208 | 2015-11-17 | Foundation Phase Profile (FPP) update | AS to communicate plans for the 2017 collection to suppliers as early as possible. | WG - AS | 2016-05-19 |  | Spec 0.1 released 19.05.16
209 | 2015-11-17 | Foundation Phase Profile - CTF proposals | CH to clarify the CTF proposal for FPP, including rules for calculation of AOLs where ladder scores are not present, and share with SDF. | WG - CH | 2016-02-02 |  | Closed as incorporated into action 230
210 | 2015-11-17 | Foundation Phase Profile - CTF proposals | CH to liaise with DFE to try and ensure FPP requirements are included in the 2016 CTF specification. | WG - CH | 2016-01-13 |  | Included in spec
211 | 2015-11-17 | Post-16 collection, matters arising from 2015 and future collections | BM to ask the funding team to clarify the purpose of collecting the Programmes of Study and associated guided contact hours. | WG - BM | 2016-02-02 |  | Paper from Geoff sent to suppliers
212 | 2015-11-17 | Post-16 collection, matters arising from 2015 and future collections | WG to clarify which pupils are to be included in the Post-16 return. | WG - CH | 2016-05-17 |  | Included in v4.0 of the 2016 specification
213 | 2015-11-17 | Post-16 collection, matters arising from 2015 and future collections | WG to provide a timeline and outline of possible changes to the 2016 Post-16 collection. | WG - CH | 2015-11-27 |  | Email from CH sent 27/11/15 giving approximate timescales for communicating any changes
214 | 2015-11-17 | Post-16 collection, matters arising from 2015 and future collections | BM to provide a detailed proposal for the replacement of Learning Activities. | WG - BM | 2016-01-19 |  | Included in WED matching paper
215 | 2015-11-17 | School workforce collection discussion paper | GT to refine the school workforce collection requirement and update SDF. | WG - GT | 2016-05-25 |  | Update and papers supplied and to be discussed at 1 June meeting
216 | 2015-11-17 | AOB - SEN classifications | CH to include new requirement for SEN needs in January PLASC specification for 2017. | WG - CH | 2016-01-19 |  | Included in spec
217 | 2015-11-17 | AOB - SEN classifications | CH to feed back ‘school concern’ suggestion to policy team. | WG - CH | 2015-11-27 |  | Policy team confirmed 'school concern' will not be collected
218 | 2016-02-02 | PLASC 2017 draft specification | WG to feedback the need for further guidance on SEN data to the policy team. | CH | 2016-03-22 |  | Raised with policy team and confirmed that guidance is not due for an update yet
219 | 2016-02-02 | PLASC 2017 draft specification | JA to send WG the Northern Irish policy on SEN reporting. | John Ashworth | 2016-06-01 |  | JA sent on 1/6/16
219 | 2016-02-02 | PLASC 2017 draft specification | JA to send WG the Northern Irish policy on SEN reporting. | John Ashworth | 2016-06-01 |  | JA sent on 1/6/16
220 | 2016-02-02 | EOTAS 2017 draft specification | CH to add LEA tag above the new Estab tag. | CH | 2016-04-01 |  | Specification updated
221 | 2016-02-02 | EOTAS 2017 draft specification | WG to arrange a separate meeting to discuss the EOTAS collection exclusions requirement. | RE | 2016-04-01 |  | Meeting no longer required. Specification issued on 01/04/2016
221 | 2016-02-02 | EOTAS 2017 draft specification | WG to arrange a separate meeting to discuss the EOTAS collection exclusions requirement. | RE | 2016-04-01 |  | Meeting no longer required. Specification issued on 01/04/2016
222 | 2016-02-02 | EOTAS 2017 draft specification | CH to amend the EOTAS specification to include various pupil scenarios for exclusions from PRUs. | CH | 2016-04-01 |  | Specification updated
223 | 2016-02-02 | Post-16 collection | WG to organise a separate meeting / telephone conference to discuss the Post-16 collection. | RE | 2016-06-01 |  | Meeting provisionally booked for 27 July and to be discussed at 1 June meeting
224 | 2016-02-02 | Post-16 2016 Specification | CH to amend specification to include DOB in section 2.1. | CH | 2016-05-17 |  | Included in v4.0 of the 2016 specification
225 | 2016-02-02 | Post-16 2016 Specification | BM to send draft completion notes to SDF for comment prior to the collection. | BM | 2016-05-17 |  | Completion notes released by MW
226 | 2016-02-02 | Post-16 2016 Specification | BM to feedback thoughts on the programme level data to the rest of the policy team. | BM | 2016-05-17 |  | Done
227 | 2016-02-02 | Post-16 2016 Specification | Suppliers to provide specific data items they suggest should be added to the mapping table. | Suppliers | 2016-06-01 |  | Feedback was provided in 1/6/16 meeting
228 | 2016-02-02 | Key Stage 4 | Wales is now diverging further from England at KS4. Suppliers to confirm that their systems are ready to implement these changes and differences. | Suppliers | 2016-10-11 |  | Feedback received from Capita. Closed at 11.10.16 meeting as no further feedback received. Agreed that suppliers would report any issues as necessary.
229 | 2016-02-02 | CTF | Suppliers to consider paper from RM and provide feedback. | Suppliers | 2016-03-04 |  | Feedback received
230 | 2016-02-02 | CTF | WG to provide SDF with rules for the transfer of FPP data. | CH | 2016-08-05 |  | Included in NAW_A_COMP 2017 v2.0
230 | 2016-02-02 | CTF | WG to provide SDF with rules for the transfer of FPP data. | CH | 2016-08-05 |  | Included in NAW_A_COMP 2017 v2.0
231 | 2016-02-02 | Hwb | Hwb presentation and documents to be sent to SDF colleagues. | RE | 2016-03-02
232 | 2016-02-02 | Modular CBDS | WG to feedback discussion on the free breakfast data item to policy team and identify what the data is used for. | CH | 2016-03-29 |  | Discussion with policy team requires further thought. Will potentially be part of a change for 2018 collection so action closed for SDF.
233 | 2016-02-02 | AOB | WG to keep the XSLT release schedule as 0, 1, 2, 3. | CH | 2016-02-24 |  | Requested changes currently being tested
234 | 2016-06-01 | Successful Futures | Review communication channels for Successful Futures as LAs report that information isn’t getting through to them via consortia | CR | 2016-11-15 |  | Advised that all information is provided to LAs via consortia. Please notify us of specific instances of delayed information to LAs.
235 | 2016-06-01 | Successful Futures | Consider how SDF could input to the development of thinking about revisions to the assessment framework and to implement a two-way process | CR | 2017-02-01 |  | No further update.
236 | 2016-06-01 | Successful Futures | Consider how SDF could input to the work in pioneer schools and their needs given the differing requirements | CR | 2017-02-01 |  | No further update.
237 | 2016-06-01 | KS4 performance reporting | suppliers to confirm they are able to meet Wales’ requirements using the pre-Woolf discount codes list, which is different to the list in England | Suppliers | 2016-10-11 |  | Closed and agreed that suppliers will report any issues.
238 | 2016-06-01 | KS4 performance reporting | WG to provide QAN list for specific qualifications where possible. | SA | 2017-02-01 |  | 06/01/17 - QANs circulated for relevant maths, English and Welsh qualifications. 01/02/16 - Science circulated.
239 | 2016-06-01 | KS4 performance reporting | WG to send link to the letter about changes to KS4 performance reporting | SA | 2016-10-06 |  | Bulletin sent on 06/10/16
240 | 2016-06-01 | KS4 performance reporting | WG to provide the methodology and a worked example for the Capped Points Score calculation. | SA | 2016-10-06 |  | Capped Points Score overview can be found here (same link as above): http://gov.wales/topics/educationandskills/schoolshome/schooldata/using-school-information-and-reporting-on-performance/?lang=en. Within this overview there is a link to a worked example in the categorisation guidance which uses the same underpinning logic.
241 | 2016-06-01 | KS4 performance reporting | WG to provide the mapping of DfE grades 1-9 to Wales’ grades | SA | 2017-05-22 |  | Letter circulated.
242 | 2016-06-01 | NDC 2017 Draft Specification | WG to consider the timing of the Baseline Assessment data collection | CH | 2016-07-29 |  | No changes for 2017 and the collection as a whole will be considered alongside the Successful Futures planning
243 | 2016-06-01 | WNT 2017 Draft Spec | CH to add ‘significance’ to Modular CBDS, NAW_A_COMP and WNT specification | CH | 2016-07-29 |  | Included in NAW_A_COMP 2017 v1.0 and WNT Specification 2017 v1.0
244 | 2016-06-01 | WNT 2017 Draft Spec | WG to relay this information to the Assessment Team | CH | 2016-06-02 |  | Concerns about infrastructure for the online adaptive tests fed back to the policy team. The Tests branch has assured us that this is all being considered as part of the project and that they are working with the Digital Unit on this.
245 | 2016-06-01 | School Workforce collection Update | WG to consider setting up an SDF to go through the School Workforce data collection requirements | CH | 2016-06-01 |  | SDF Workforce Workshop scheduled to take place end of June/mid July 17.
246 | 2016-06-01 | AOB | MJ raised an issue regarding categorisation of EAL pupils to Capita. MJ informed the group that there is disparity between the English and Welsh models and Capita still allows ‘ENG’ to be used as home language. | WG | 2017-06-27 |  | Action closed due to no further information being supplied.
247 | 2016-06-01 | AOB: Class Size Exception Codes | CH to include changes in Modular CBDS and January PLASC 2017 specification. | CH | 2016-06-02 |  | Included in Modular CBDS v1617.1 School and PLASC 2017 specification v2.0
248 | 2016-10-11 | Minutes and actions of last meeting | WG to ensure guidance for the timing of the BA assessments for the collection is clear | WG - AS | 2017-02-01 |  | NDC Completion Notes.
249 | 2016-10-11 | School performance reporting update | WG to check if the QiW export file includes details of when it was last updated and how | WG - SA | 2016-11-15 |  | Export file includes details of when last updated but now how.
250 | 2016-10-11 | School performance reporting update | WG to look into the possibility of having MIS specific exports from QiW to help with development | WG - CH | 2017-06-28 |  | Action closed as extract has now been agreed and supplied.
251 | 2016-10-11 | School performance reporting update | Suppliers to inform WG of their requirements for an export file from QiW by 31/10/16 | WG - CH | 2017-06-22 |  | Requirements received from Capita
252 | 2016-10-11 | School performance reporting update | WG to confirm that archived qualifications are included in the export file from QiW | WG - SH | 2016-11-15 |  | Yes. 2 options - 1. All archived quals excluded. 2. Advanced search - incl. archived qualifications.
253 | 2016-10-11 | School performance reporting update | WG to clarify if Attendance forms part of the statutory target setting requirements | WG - SA | 2016-11-15 |  | Yes. Included in The School Performance and Absence Targets (Wales) Regulations 2011. Link http://www.legislation.gov.uk/wsi/2011/1945/made
254 | 2016-10-11 | School performance reporting update | WG to confirm if discount codes are required at Post-16 | WG - SA | 2016-11-15 |  | Currently required and no plans to change.
255 | 2016-10-11 | Post-16 2018 draft specification | WG to update worked examples in the specification and the completion notes to ensure the requirement is clear | WG - MW | 2016-11-22 |  | Examples updated.
256 | 2016-10-11 | Post-16 2018 draft specification | WG to consider how best to link activities to programmes | WG - MW | 2016-11-23 |  | Programme ID will be used for submission purposes. 001-1000
257 | 2016-10-11 | Post-16 2018 draft specification | WG to clarify field length for Programme Reference and consider additional item for Programme Extension code if it is required. | WG - MW | 2016-11-24 |  | 8 Char
258 | 2016-10-11 | Post-16 2018 draft specification | WG to reconsider the code for when a programme is transferred to a new provider and contemplate ways of ensuring the code is not used to falsely report on withdrawals | WG | 2017-06-23 |  | Code 5 'transferred to a programme with a different provider' confirmed. Included in Modular CBDS 1718
259 | 2016-10-11 | Post-16 2018 draft specification | WG to include guidance on pupils who leave school and then return. | WG - MW | 2017-06-23 |  | Guidance has been added to the 2017 completion notes
260 | 2016-10-11 | Post-16 2018 draft specification | WG to clarify if ‘/’ characters are required in the Qualification Wales Approval/Designation Number | WG - MW | 2016-11-22 |  | In line with request at SDF 11 Oct '/' should be removed when stored or submitted
261 | 2016-10-11 | Post-16 2018 draft specification | WG to look into date fields included in the QiW export file and ensure their clarity and usefulness | WG - SA | 2017-02-01 |  | Roll into action 272
262 | 2016-10-11 | Post-16 2018 draft specification | WG to confirm when and if the programmes list will be altered, ensuring early notice to schools | WG - GH | 2017-02-01 |  | Programme list remaining unchanged.
263 | 2016-10-11 | Post-16 2018 draft specification | WG to clarify the definition of resit and retake and provide guidance on how these should be treated for the Post-16 collection | WG - MW | 2016-11-02 |  | Clarification added to 2017 Technical Completion notes. • • If a pupil does whole activity again (i.e. takes the same teaching and learning activity two years in a row) then this activity is recorded again in the second year. • However, if the only thing that the pupil does is sit the same exam again (twice, or more) for any reason, that should not be recorded as a learning activity at all as part of a programme.
264 | 2016-10-11 | XSLT versioning | WG to consider suggestions for changes to the XSLT process | WG - CH | 2016-11-15 |  | Changes to the xslt process tabled and agreed a the SDF meeting.
265 | 2016-10-11 | XSLT versioning | Suppliers to report any issues with filesets immediately so that they can be corrected at the time | Suppliers | 2017-02-02 |  | Agreed at SDF meeting to close as it is an ongoing process.
266 | 2016-10-11 | AOB | WG to clarify process for getting a URN and ensure this is as efficient as possible | WG - CH | 2017-11-07 |  | Draft provided at 7 November 2017 meeting
268 | 2016-10-11 | AOB | WG to review the need for Completer Hours across all collections | WG | 2017-03-06 |  | Currently required as being used to review burdens.
269 | 2016-10-11 | AOB | WG to ensure the correct term ‘Year’ or NCYear’ is used in guidance across all collections | WG | 2017-02-01 |  | Added to all change logs and being actioned for each specification and set of guidance notes as they are updated.
270 | 2016-11-15 | School performance reporting | Discount code field length to be confirmed | WG | Moved to Performance Actions tab |  | 20/02/18 - performance/qualifications meeting Steve Hughes leading on this. He had a positive meeting with JCQ last week. Update to be provided
271 | 2016-11-15 | School performance reporting | Confirm how far back the qualification archive will cover in QiW | WG | Moved to Performance Actions tab |  | 7/11/17 - performance/qualifications meeting
272 | 2016-11-15 | School performance reporting | Data definition document for QiW to be provided | WG | Moved to Performance Actions tab |  | 20/02/18 - Qualifications Wales have prepared data definitions document. If there are any gaps identified, the document can be adapted and expanded over time.
273 | 2016-11-15 | Post-16 2018 draft specification | Clarify if the ‘expected start and end dates’ in the new programme container are needed. | WG | 2017-06-07 |  | The start and end date of the programme are required as these are key fields for funding to identify if they have been there for 8 weeks or not.
274 | 2016-11-15 | Post-16 2018 draft specification | Provide guidance on whether pupils in a special unit within a mainstream school should be included in the return | WG | 2017-06-23 |  | All pupils who are 'M' or 'C' with the school should be included. This will include any in a special unit if the pupils are 'M' or 'C'. Will be added to the 2017 Questions and Answers document.
275 | 2016-11-15 | Post-16 2018 draft specification | Confirm if when the 2nd year of a programme goes into a 3rd academic year, the year of the programme should be recorded as 2nd or 3rd | WG | 2017-06-07 |  | If undertaking any teaching or learning from year 2 in a 3rd year in order to repeat or redo the year or exam, this would be recorded as code 3 (Year 3+) for 'year of programme'.
276 | 2016-11-15 | Post-16 2018 draft specification | If a pupil redoes part of a year, confirm what the cut-off is between just redoing the exam or redoing the teaching and learning | WG | 2017-06-23 |  | The distinction isn’t to do with the amount of time; it’s whether the learner is undertaking any additional learning activity. If so, the record should be submitted. We want the schools to submit all learning activities that are delivered regardless of their duration. • If the learner is not undertaking any teaching and learning and is only retaking an exam, no record is required as there is no learning activity, just an award. See also 263.
277 | 2016-11-15 | Post-16 2018 draft specification | Provide guidance/ rules to derive Main/Other so that suppliers can look to provide an ‘estimate’ within their systems for schools to then update if necessary. | WG | 2016-11-30 |  | Response provided to Capita. Query 993.
278 | 2016-11-15 | Post-16 2018 draft specification | Consider adding the rules for Main/Other into validation rules | WG | 2017-09-01 |  | Considered for Validation CBDS v1718.3 but not implemented
279 | 2017-02-02 | Post-16 2018 draft specification | Confirm how Learning Provider and Learning Activity lists will be provided | WG | 2017-05-04 |  | Information provided in 2018 specification v0.3
280 | 2016-11-15 | Post-16 2018 draft specification | Consider if the XML tag for the Learning Activity should be changed to the QWAD and if this will give enough definition | WG | 2017-05-04 |  | Agreed
281 | 2016-11-15 | Post-16 2018 draft specification | A new tag should be introduced for the new codes | WG | 2017-05-04 |  | Agreed
282 | 2016-11-15 | AOB | Consider if a mapping/amendments to any mapping to the DfE language codeset is needed | WG | 2017-06-14 |  | Included in Modular CBDS_1718
283 | 2016-11-15 | AOB | Consider if a mapping/amendments to any mapping to the DfE ethnicity and language source codesets is needed | WG | 2017-06-14 |  | Included in Modular CBDS_1718
284 | 2017-02-02 | School performance reporting update | SH confirmed four digit codes for the new mathematics GCSEs and feedback to the group. | WG-CH | 2017-05-26 |  | School Performance Reporting bulletin No. 3' 24/05/17 http://gov.wales/topics/educationandskills/schoolshome/schooldata/using-school-information-and-reporting-on-performance/?lang=en
285 | 2017-02-02 | School performance reporting update | Capita to produce guidance for schools for adding new discount codes into the ‘base data’ | Capita | 2017-06-27 |  | Guidance has been added by Capita
286 | 2017-02-02 | School performance reporting update | WG to contact JCQ and contacts at the Federation of Awarding Bodies. | WG-CH
287 | 2017-02-02 | School performance reporting update | MJ to send details of specific examples of qualifications on QiW that are missing points data. | MJ | 2017-06-27 |  | All anomalies reported have been clarified or rectified
288 | 2017-02-02 | School performance reporting update | CH/ MJ or others to advise WG of any invalid grade sets identified in QiW. | All | 2017-06-27 |  | All anomalies reported have been clarified or rectified
289 | 2017-02-02 | School performance reporting update | WG to speak to Gwion Dafydd about possible use of a capped points score spreadsheet. | WG |  |  | 7/11/17 - performance/qualifications meeting
290 | 2017-02-02 | PLASC and EOTAS 2018 Draft Specification | Consider adding a suggestion for a prompt message in the specification and in systems (WG & Suppliers) | WG / Suppliers | 2017-06-29 |  | Added to v1.0 of the spec released on 29 June 2017
291 | 2017-02-02 | PLASC and EOTAS 2018 Draft Specification | Consider adding a validation rule to try and alert schools to invalid free school breakfast data if 2017 PLASC data still shows some issues. | WG | 2017-06-27 |  | New validation added to Validation CBDS v1718.2.0
292 | 2017-02-02 | PLASC and EOTAS 2018 Draft Specification | WG to consider adding validation to stop invalid combinations of SEN needs. E.g. ALD and SLD | WG | 2017-06-27 |  | New validation added to Validation CBDS v1718.2.0
293 | 2017-02-02 | PLASC and EOTAS 2018 Draft Specification | Provide common PLASC/ Catholic School census questions (Capita) | Capita | 2017-11-03 |  | Document received from Capita 03/11/17
294 | 2017-02-02 | PLASC and EOTAS 2018 Draft Specification | Investigate if PLASC/Catholic School census data can be combined or shared | WG |  |  | Combined with 313
295 | 2017-02-02 | PLASC and EOTAS 2018 Draft Specification | Respond to query about the application of rule 750Q in two schools. | WG | 2017-06-27 |  | Query responded to and amendments made in Validation CBDS v1718.2.0
296 | 2017-02-02 | PLASC and EOTAS 2018 Draft Specification | Amend specification to clarify if free breakfast data is ‘prior’ or ‘during’ census week. | WG | 2017-06-27 |  | New validation added to Validation CBDS v1718.2.0
297 | 2017-02-02 | PLASC and EOTAS 2018 Draft Specification | Class size exceptions - Consider further with the policy lead | WG | 2017-06-27 |  | New validation added to Validation CBDS v1718.2.0
298 | 2017-02-02 | AoB | 2018 Science spreadsheet to be circulated. | WG-CH | 2017-07-11 |  | 2018 spreadsheet sent
299 | 2017-06-27 | School performance reporting update | WG to schedule performance / exams update for future SDF meetings and invite interested parties from QW, JCQ, A2C | WG | 2017-11-07 |  | Afternoon session of SDF on 7th November dedicated to qualifications, performance and exams
300 | 2017-06-27 | NDC 2018 Draft Specification | WG to look into using year UPN was issued as a possible validation check for NEWBES status | WG | 2017-09-01 |  | Considered for Validation CBDS v1718.3 but not implemented
301 | 2017-06-27 | WNT 2018 Draft Specification | WG to amend NDC specification to reflect the NEWBES guidance in the WNT specification | WG |  |  | 7/11/17 - Will be released with 2 further minor updates.
303 | 2017-06-27 | Online personalised tests overview | RM to supply more information to WG about SIMS Single ID | Capita | 2017-06-01 |  | Information provided by Rachael June 2017
305 | 2017-06-27 | Post-16 2017 additional xslt and Post-16 2018 draft specification | WG to provide QWAD list to suppliers | WG | 2017-06-28 |  | QWAD extracts provided on DEWi
306 | 2017-06-27 | Post-16 2017 additional xslt and Post-16 2018 draft specification | WG to provide decision trees to suppliers | WG | 2017-11-07 |  | Will be provided in completion notes
307 | 2017-06-27 | AoB | WG to clarify in guidance the new categories for Ethnicity | WG | 2017-10-01 |  | Provided in PLASC and EOTAS completion notes for 2018
308 | 2017-06-27 | AoB | WG to clarify in guidance that all pupils must have a SEN status | WG | 2017-10-01 |  | Provided in PLASC and EOTAS completion notes for 2018
309 | 2017-06-27 | AoB | WG to confirm if schools are legally required to have a website | WG | 2017-11-28 |  | Email received from Estyn 28/11/17 - No schools arent leaglly required to have a website.
310 | 2017-11-07 | Actions | See 266 - Comments on the draft process for acquiring URNs to be provided | All |  |  | No comments have been provided
312 | 2017-11-07 | Actions | Discussions to take place with DfE with a view to improve access to s2s | WG | 2018-02-22 |  | Some discussions have taken place, Jayne to continue talks with DfE
313 | 2017-11-07 | Actions | See 293 - Scope for data sharing between PLASC and the Catholic School Census to be assessed | WG |  |  | Combined with Action 294 Email received from John Ashworth
314 | 2017-11-07 | School workforce | The specification to confirm if contracts are required | WG | 2018-06-07 |  | This will be in the spec but it will be from LA's/multiple LA's
315 | 2017-11-07 | School workforce | Differences between 'post' and 'role' to be clarified in the specification (WG) | WG | 2018-06-07 |  | Provided in the spec, (schools and LA's input)
316 | 2017-11-07 | School workforce | Clarification of contracts to be provided in the specification to include who holds the contract - the school of the LA | WG | 2018-06-07 |  | This will be from LA's unless its an opted out school
317 | 2017-11-07 | School workforce | The capture and possible ascription for 'Ethnicity' and 'National Identity' data to be included in guidance | WG | 2018-06-07 |  | For the spec and guidance notes. Drawing from PLASC collection.
318 | 2017-11-07 | School Workforce | The recording of multiple roles, potentially across multiple schools, phases and medium of delivery to be included in guidance | WG | 2018-06-07 |  | Recorded separately
319 | 2017-11-07 | School workforce | LA's to be involved in discussions about School Workforce data collection | WG | 2018-06-07 |  | Workshop sessions throughtout Wales - feedback to be provided
320 | 2017-11-07 | School workforce | Test environment and training data to be provided | WG | 2018-06-07 |  | This will be built into the development plan
321 | 2017-11-07 | School workforce | SDF were requested to review the paper and send all comments in as soon as possible to inform the development of the collection | All | 2018-06-07 |  | No comments have been received
322 | 2017-11-07 | Curriculum and Assessment update | Links to further information on the new curriculum development to be provided | WG |  |  | Manon Jones has provided the links below: Our website: http://gov.wales/topics/educationandskills/schoolshome/curriculuminwales/curriculum-for-wales-curriculum-for-life/?lang=en Our blog: https://curriculumforwales.gov.wales/
326 | 2017-11-07 | AOB | WG to send an update on the implementation of IDPs | WG | 2018-02-22 |  | On agenda 22/02/18 - Paper provided by Andrew Nicholas
327 | 2017-11-07 | AOB | WG to provide an update on the 30 hour pilot for free child care | WG | 2018-02-22 |  | Email received from Nicola Edwards with update
328 | 2018-02-22 | Actions | AM to speak to relevant WG contact to explain the link between FSM and Universal credit | WG | 2018-06-20 |  | Emailed Lowri Reed. Lowri provided a detailed paper that can be passed round to SDF colleagues if requested.
329 | 2018-02-22 | SWAC | Can DEWi look at reports and give comparisons? | WG |  |  | Method4 - speak with them
330 | 2018-02-22 | Post-16 | Provide schools with guidance on the new Post-16 structure | WG | 2018-06-15 |  | The new Completion Notes and FAQs have been uploaded to the WG website. An email has been sent to all IMS contacts advising that they have been updated and released. LAs now need to now communicate with their schools.
331 | 2018-02-22 | SWAC | SWAC team to work with the Equality team to define these terms appropriately. |  | 2018-06-20 |  | 20/06/18 - On going
333 | 2018-02-22 | Performance Reporting | WG to proivde SDF with powerpoint presentation from Head teacher conference | WG | 2018-06-15 |  | http://learning.gov.wales/news/events/national-education-conference-for-secondary-headteachers-and-key-stakeholders/?lang=en link attached with presentation and more information
334 | 2018-02-22 | Performance Reporting | Can the Capita system record G, S, Z | PW (Capita) | 2018-06-15 |  | Currently we cannot record this as it was not part of the NAW _Comp specification so was not built into the welsh resources. We can amend the resources for future releases to accommodate a wider grade set which could include G, S and Z (and/or the W grade which is currently available). There are also a number of other options we could employ to allow the school to record one value but transpose this to another value which would be sent to the Welsh Government. IE if we see a G,S or Z grade in the schools data we could send a W value in the upload sent to Welsh Gov. There may also be other ways around it which I will not bore you with. Whichever option we choose of course we would need to agree with both WG and schools to ensure we meet all requirements going forward and in such a way as could be easily maintained.
335 | 2018-02-22 | AOB | AS to consider the issues discussed before communicating submission requirements to schools and local authorities. AS to confirm agreed action for the NDC collection. | AS (WG) | 2018-06-15 |  | The submission requirements were confirmed when the NDC completion notes went out (see emails to LAs below). I am also changing the requirements for NDC 2019 (which they will see in the draft spec) to collect all codes
336 | 2018-02-22 | PLASC and EOTAS 2018 Draft Specification | Update of Service Children | WG | 2018-06-15 |  | With the Policy Team presently, chases to legislation cant be put through until after Brexit so will be put on hold for the time being
337 | 2018-02-22 | Additional Learning Needs and Education Tribunal (Wales) Act 2018 and IDPs | Clarification of whether IDPs will be electronic | WG (ALN Policy Team) |  |  | There will be no statutory or policy requirement for electronic IDPs. The Act requires an agreed form or forms for the IDP. Any decisions on producing and maintaining electronic versions of IDPs will be a matter for schools/local authorities/regional consortia.
338 | 2018-02-22 | Additional Learning Needs and Education Tribunal (Wales) Act 2018 and IDPs | Can IDPs be appealed and are there regulations on this. | WG (ALN Policy Team) |  |  | There are - detail is already provided in the Act and drafts code - the next iteration of the code and a suite of regulations will provide more detail, particularly around the Education Tribunal for Wales (which is replacing SENTW). There are a range of appeal and reconsideration routes available before cases are escalated to ETW level.
339 | 2018-02-22 | AOB | WG to look at CBDS | WG (JHo) | Ongoing |  | Currently being looked at by team
348 | 2018-06-26 | WNT | WG to release v0.1 of WNT 2019 spec as soon as possible after the meeting | WG | 2018-06-29 |  | 29/06/2018 - Uploaded to SDF
349 | 2018-06-26 | Post-16 | GE to release v1.0 of the Post-16 Spec following the SDF meeting | WG/GE | 2018-06-29 |  | 29/06/2018 - Uploaded to SDF
350 | 2018-06-26 | Post-16 | JT to correspond with GE on the example referred to re closing schools | JT/GE | 2018-06-29 |  | JT sent GE email and saved to SDF actions folder with number
364 | 2018-06-26 | SWAC | Remove former family names from spec – considered to be not useful and often not available. | WG | Moved to SWAC Actions tab |  | GTh has removed this
372 | 2018-06-26 | SWAC | SDF site of DEWi – add SWAC collection items e.g. Spec, Modular CBDS. | WG | Closed
PR-001 | 2016-11-15 | School performance reporting | Discount code field length to be confirmed | WG (SH) | Closed | 2019-10-01
PR-002 | 2016-11-15 | School performance reporting | Confirm how far back the qualification archive will cover in QiW | WG | Closed |  | Qualifications Wales have confirmed that qualifications remain on QiW and within the archive, indefinitely.
PR-003 | 2016-11-15 | School performance reporting | Data definition document for QiW to be provided | WG | Closed |  | 20/02/18 - Qualifications Wales have prepared data definitions document. If there are any gaps identified, the document can be adapted and expanded over time. 16/10/18 - Data definition document for Qualifications in Wales (QiW) to be provided. SA told all that the document is now on the webpage and that there is also a user guide on the Welsh Government’s website.
PR-004 | 2017-11-07 | Performance measures changes | Group to feedback comments about the information supplied and highlight any gaps or issues with interpretation | All | Closed |  | Closed.
PR-005 | 2017-11-07 | Performance measures changes | WG to set up links with QW and suppliers to enable API discussions | WG | Closed |  | A QiW user group meeting has been set up by Qualifications Wales and software suppliers are welcome to join. We circulated the invite email last year. Closed.
PR-006 | 2017-11-07 | A new discounting system | Suppliers to investigate use of discount codes as stored on QiW, including those greater than 4 characters in length, and to feedback any issues to WG. | Suppliers | Closed | 2019-10-01 | discount codes for QN/QWAD code variations can be found in a spreadsheet published on the WG web pages.
PR-007 | 2017-11-07 | AOB | WG to set up twice yearly meetings of this group | WG | Closed |  | Close. Discussions included as part of SDF. Separate meetings to SDF to go through PR to be arranged.
PR-008 | 2018-02-22 | Performance Reporting | WG to provide further information on Performance Measures for development cycle | WG | Closed |  | Performance Reporting Bulletin 6 will be published next week and will be distributed to the SDF group. Distributed on 7th February 2019.
PR-009 | 2018-06-26 | Performance Reporting | WG to provide a link to Performance Measures bulletin from May 2018 | WG | Closed |  | Closed - has been circulated The Welsh Government to provide a link to performance measures bulletin from May 2018. SA said this has now been circulated via email to all.
PR-010 | 2018-06-26 | Performance Reporting | Send out changes to the Capped Points Score document | WG (SA/SH) | Closed | 2019-10-01
PR-011 | 2018-06-26 | Performance Reporting | AMi to provide some further details in relation to the socio-economic breakdown of schools | WG (SA/SH) | Closed | 2019-10-01
PR-012 | 2019-02-07 | Performance Reporting | WG need to speak to Qualifications Wales and WJEC about base data origins and understand fully why it is needed. | WG (SH/SA) | Closed | 2019-10-01
PR-013 | 2019-02-07 | Performance Reporting | SH to clarify the QANs/QWADs used for discounting | WG (SH) | Closed | 2019-10-01
PR-014 | 2019-02-07 | Performance Reporting | SH to provide a list of which qualifications would discount others to Capita | WG (SH) | Closed | 2019-10-01
SDF-302 | 2017-06-27 | Online personalised tests overview | WG to confirm LA involvement in online assessments | WG | Closed |  | 14/02/18 - No further update as yet
SDF-304 | 2017-06-27 | Online personalised tests overview | WG to confirm Hwb integration and data flows | WG | Closed |  | 14/02/18- No further update as yet
SDF-311 | 2017-11-07 | Actions | See 266 - WG to provide a final version of the URN process document | WG | Closed |  | Final document should be available by w/c 19/02
SDF-323 | 2017-11-07 | Curriculum and Assessment update | Workshop session on curriculum development and recording progress to be arranged in the new year | WG | Closed |  | 14/02/18 - No further update // 07/03/19 - Discussed in AOBs in meeting of 07/03/19
SDF-324 | 2017-11-07 | Curriculum and Assessment update | SDF to be updated with the naming convention for recording pupil progress to ensure consistency across systems | WG | Closed |  | 14/02/18 - No further update // 07/03/19 - Discussed in AOBs in meeting of 07/03/19
SDF-325 | 2017-11-07 | AOB | Requirement for information from Department of Health to be investigated with a view to reducing burdens and removing any duplication | WG | Closed | 2019-10-01 | This issue has not rised since 2017, so the action will be closed unless the issue arises again.
SDF-343 | 2018-06-26 | NDC | AS to confirm whether comparative reports will be removed | WG/AS |  |  | Yes, comparative reports with benchmarking will no longer be produced.
SDF-344 | 2018-06-26 | NDC | AS to discuss specific concerns/examples of BA validation and data to be captured and possible resolutions with Mike Jones | WG/AS | Closed |  | Mike has passed on examples and his ideas for resolution to AS. A separate communication from WG will follow on the issue soon.
SDF-345 | 2018-06-26 | NDC | WG to consider whether there is a need to add rules to Validation CBDS to check if BA is present and to check the dates | WG | Closed |  | AS has considered, but feels that new validation rules could potentially still miss incorrect data. (email to confirm this)
SDF-346 | 2018-06-26 | NDC | AS to update NDC 2019 spec to add clarification surrounding what BA data is being used for. | AS | Closed |  | Not yet added to the spec. AS intends to include this information when the NDC completion notes are issued.
SDF-347 | 2018-06-26 | NDC | AS to look at progression steps for AoLs and feed back to group. | AS | Closed |  | AS will email this action out.
SDF-351 | 2018-06-26 | Post-16 | SIIB to invite Post-16 colleagues to next SDF | WG | Closed - 07/02/19 |  | On-going - to attend next meeting
SDF-352 | 2018-06-26 | AOB | Updated terms of reference to be circulated. | JHo | Closed 16/10/18 |  | Agenda item we'll look at today 16/10/18
SDF-353 | 2018-06-26 | AOB | GTh to consider whether to arrange a future event specifically to cover SWAC | WG/GTh | 2018-10-12 |  | SWAC workshop took place on 12/10/2018
SDF-354 | 2018-06-26 | AOB | Follow up EOTAS Pupil Registration paper feedback. | WG | Closed | 2019-10-01 | Pupil registration is on the agenda for 17 October 2019
SDF-355 | 2018-06-26 | AOB | Check validation rules for attendance collection | GE | Closed |  | Completed and XSLT work done and tested, though yet to add in this specific element about codes D and B and need to discuss with policy. Completed
SDF-356 | 2018-06-26 | AOB | SIIB colleagues to check with ALN colleagues and seek clarification on whether pupils have a legal right to appeal their IDPs. | WG | Closed |  | We have a brief update from colleagues, we'll need to look at this with policy colleagues further. On agenda 07/03/19
SDF-357 | 2018-06-26 | AOB | WG to speak to DfE about CTF developments and having the new IDP codes added. | GE | Closed |  | DfE have been made aware of the upcoming changes that will be required for the CTF20 spec.
SDF-359 | 2018-06-26 | AOB | SIIB to explore whether it is possible for LRS to generate CTFs to make importing ULNs into MIS systems easier for schools. | WG | Closed | 2019-07-12 | Ongoing as part of discussions and duplicated in SDF-358 so this item is closed.
SDF-360 | 2018-10-16 | NDC | AS to confirm and send update out regarding any change of date for BA data collection | WG/AS | Closed |  | BA data will be collected at the same time as other teacher assessment data this year. (NDC date on roll: 14 May 2019). Concerns had been raised previously at SDF that some schools were using an assessment system that was exporting a pupil’s latest assessment on the Foundation Phase Profile (FFP) to MIS, as opposed to their BA. It was suggested that an earlier collection of BA would allow schools to return this statutory assessment soon after completion and decrease the risk of later FFP assessments being sent. It has since been reported that the assessment system in question now freezes BA for export. Therefore an earlier collection of BA data will no longer be considered. The collection will remain at the end of the year to ensure that all BAs that happen throughout the year are gathered.
SDF-361 | 2018-10-16 | Actions | WG to look into codes D and B being misused by schools and explore the idea of having a rule that triggers a query when a certain % of codes are entered | WG | Closed - 07/02/19 |  | Attendance Policy lead to attend SDF on 7th February
SDF-362 | 2018-10-16 | PLASC | WG to send official confirmation out regarding changing gender to sex | WG | Closed |  | Conversations still ongoing, but this should be implemented for SWAC 2019.
SDF-363 | 2018-10-16 | Universal Credit | All to consider Universal Credit paper from MD and provide feedback | All | Closed
SDF-364 | 2018-10-16 | Performance Reporting | GE to speak to capita regarding new QWAD code list | WG/GE | Closed |  | Suppliers to extract the data themselves and create a list.
SDF-365 | 2018-10-16 | OPAs | AT to send out possible options to all regarding teacher category on Hwb | WG/AT | Closed |  | Complete. A follow up meeting with workforce and Hwb colleagues on 3rd December 2018, agreed the teacher categories required for Personalised Assessment is already available as part of the workforce collection. Completion notes and subsequently CBDS already have this information. No specific / additional categories are requested. As the completion notes and CBDS are being circulated no need for further clarification.
SDF-365 | 2019-02-07 | Minutes, actions, matters arising | Update minutes from 16 October 2018 to correct first name. | WG | Closed |  | CH amended minutes and has uploaded to SDF pages of DEWi
SDF-366 | 2018-10-16 | OPAs | GTh to send JDi CBDS | WG/GTh | Closed |  | Internal WG
SDF-367 | 2018-10-16 | Attendance | WG will summarise notes from policy team and send out to all SDF attendees | WG | Closed |  | Yes, followin SDF meeting on 16th October.
SDF-370 | 2019-02-07 | Post-16 | BM to look at what feedback has gone back to local authorities (on wrong QWAD codes) | WG/BM | Closed
SDF-371 | 2019-02-07 | Post-16 | SIIB to look at creating workshops with BM | WG (GE/BM) | Closed |  | On agenda to be discussed at 6 february 2020 meeting to arrange a workshop
SDF-372 | 2019-02-07 | PLASC/EOTAS | GE to double check with policy colleagues and get clarity on any exemptions from Universal Credit | WG/GE | Closed |  | 04/06/19 - policy colleagues have responded to query about any exemptions to LAs
SDF-374 | 2019-02-07 | PLASC/EOTAS | WG to explore whether a separate S2S-like system for Welsh Schools and local authorities is feasible | WG (GE) | Closed | 2019-10-01 | This is now being taken forward
SDF-375 | 2019-02-07 | PLASC/EOTAS | WG to look at this and consider the XML tags | WG | Closed |  | Rolled back any changes so action now resolved
SDF-376 | 2019-02-07 | PLASC/EOTAS | WG need to consider what would happen with existing data where there is only one <Gender> field and whether this could be mapped to new new <Sex> item within MIS and for CTF transfers. | WG | Closed |  | Rolled back any changes so action now resolved
SDF-377 | 2019-02-07 | PLASC/EOTAS | GE to confirm implementation as soon as possible and have something in writing | WG | Closed |  | Rolled back any changes so action now resolved
SDF-378 | 2019-02-07 | AOBs | SIIB to invite ALN colleagues to the next SDF meeting for an update | WG | Closed |  | Closed, Bethan Cowan joined us for discussions on 07/03/19
SDF-378 | 2019-03-07 | Minutes, actions and matters arrising | JD asked if there would be guidelines for the rechecking of Universal Credit and Free School Meals. | WG | Closed |  | Policy colleague have communicated with all LAs on processes
SDF-379 | 2019-03-07 | Sex and Gender | WG to define in guidance notes what is meant by the tag sex. | WG | Closed |  | Will be included in the upcoming technical completion notes in June 2019
SDF-380 | 2019-03-07 | Sex and Gender | WG will clarify the definitions in technical completion notes and modular CBDS | WG | Closed |  | Will be included in the upcoming technical completion notes in June 2019
SDF-381 | 2019-03-07 | FSM and Transitional Protection | GE to discuss this with policy colleagues. | WG | Closed |  | Policy colleague have communicated with all LAs on processes
SDF-382 | 2019-03-07 | PLASC/EOTAS | WG to arrange PLASC lessons learned workshop. | WG | Closed |  | Took place on 26 April 2019
SDF-383 | 2019-03-07 | PLASC/EOTAS | Method4 to check if there is a bug in the summary reports in PLASC (ethnicity) | Method4 | Closed | 2019-07-04 | James Hornby confirmed in 4 July 2019 SDF meeting that this has been resolved
SDF-384 | 2019-03-07 | s2s and Terms of Reference | WG to send email out to all LAs/IMS contacts regarding feedback on s2s | WG | Closed |  | Email circulated and responses received, main response from Mike Jones
SDF-385 | 2019-03-07 | Terms of Reference | WG to speak to FFT. | WG (GE) | Closed | 2019-08-01 | An invite to SDF and chasers have been sent to FFT
SDF-386 | 2019-03-07 | Curriculm and assessments | A workshop between curriculum policy colleagues and suppliers to be set up for future requirements. | WG | Closed |  | Curriculum colleagues will be attending on 6 February 2020 and it is on the agenda. Following this discussion, there will be a decision on whether workshops are required.
SDF-387 | 2019-03-07 | ALN | WG to look at those pupils who come from England on census week. | WG (BC) | Closed | 2020-01-30 | An EHCP does not equate to an IDP. If the LA decides when the pupil arrives that (s)he has ALN then they’d record IDP
SDF-388 | 2019-03-07 | ALN Update | ALN to be a standing agenda item as it is rolled out | WG | Closed | 2019-10-01 | This has now been added to the agenda from 17 October 2019
SDF-389 | 2019-03-07 | PLASC/EOTAS | The Welsh Government to look at clarifying guidance on using the N code for SEN in the Technical Completion Notes. | WG (GE) | Closed | 2020-01-13 | PLASC Completion Notes have been issued
SDF-390 | 2019-03-07 | ALN | BC to consider code set option for pending and appeals relating to IDPs | WG (BC) | Closed | 2020-01-30 | We don’t require this information but LAs may wish to include this as part of their own recording arrangements. If a learner has ALN then they have an automatic entitlement to an IDP and should, therefore, be recorded as having an IDP even if that IDP is pending or subject to appeal.
SDF-391 | 2019-03-07 | AOB | The Welsh Government to share a SDF development cycle in MS Project format in the coming weeks | WG (GE) | Closed | 2020-02-06 | This was shared with suppliers for the February meeting.
SDF-392 | 2019-03-07 | AOB | Welsh Government to raise the issue with the ADEW Admissions Group and note data security requirements | WG | Closed |  | 04/06/19 - GE has been invited to the next ADEW Admissions Group to discuss data security requirements
SDF-395 | 2019-04-26 | PLASC | JT to ask the Welsh SIMS User Group about cashless catering in relation to FSM eligibility and transitional protection. | JT | Closed |  | 04/06/19 - on agenda for SIMS User Group for 5 June 2019
SDF-396 | 2019-06-04 | PLASC | Capita to explore and resolve issue of a bug in the summary reports for PLASC. | Capita | Closed |  | This action is still ongoing.
SDF-397 | 2019-06-04 | SWAC | The Welsh Government will assess options available to ensure data subjects receive privacy notice and communicate on this with local authorites. | WG | Closed | 2019-07-12 | The Welsh Government has circulated a letter to all LAs on 12 July 2019 with advice about the privacy notices and it's circulation.
SDF-398 | 2019-06-04 | SWAC | The Welsh Government to speak to Hwb team about the issue of things being migrated onto Hwb and dealing with name changes. | WG | Closed |  | WG have discussed with the Hwb team and made them aware of issues.
SDF-399 | 2019-06-04 | SWAC | The Welsh Government will look at adding in a paragraph about FTE/hours for support staff to add clarity to the completion notes | WG | Closed |  | This has been added to the Technical Completion Notes
SDF-400 | 2019-06-04 | SWAC | The Welsh Government to look at whether head of school should be changed to an additional role. | WG | Closed |  | The head of school role is already within additional roles.
SDF-401 | 2019-06-04 | SWAC | The Welsh Government to confirm the process of uploading files for SWAC and whether the local authorities will be uploading their files first | WG | Closed | 2019-07-15 | The Welsh Government has considered this and will implement it as part of the pilot. LAs will be uploading first and there will also be a script of the process.
SDF-403 | 2019-06-04 | SWAC Pilot | The Welsh Government will put a timetable together for the pilot process. Beta version should be used to clone schools database. | WG | Closed |  | On agenda for 4 July 2019 meeting
SDF-404 | 2019-06-04 | WNT | The Welsh Government to get clarity and confirmation on whether any standardised scores will be made available for online personalised assessments for 2018/19. | WG | Closed |  | Following discussions with policy, there is no intention to be sharing any standardised scores from the online personalised assessments.
SDF-405 | 2019-06-04 | WNT | The Welsh Government to feed back the issues to the policy colleagues responsible for online personalised assessments. | WG | Closed |  | The Welsh Governmen has discussed thee issues with policy colleague who are already aware of them and are looking into the issues.
SDF-406 | 2019-06-04 | S2S | The Welsh Government to communicate with DfE to escalate issues relating to S2S. | WG | Closed | 2019-07-15 | Letter sent from Steve Vincent to equivalent in DfE
SDF-407 | 2019-06-04 | AOB | The Welsh Government to chase up with colleagues and confirm when the next performance bulletin is released. | WG (SA) | Closed | 2019-10-01 | interim measures) and how we are planning to provide this data to schools has been communicated and published in the guidance released on 30/06/2019
SDF-408 | 2019-07-04 | SWAC | Pilot. Query on whether real school number should be used or if the pilot was tested using SDF site – WG to consider and confirm which option is feasible | WG | Closed | 2019-08-05 | Pilot will be carried out on the DEWi Test Site
SDF-409 | 2019-07-04 | FSM/TP | The Welsh Government to share RV’s email on the algorithms for catering systems with the minutes of the meeting. | WG (GE) | Closed | 2019-08-12 | Ruth sent the email on 12/08/19 - this went out with the SDF minutes
SDF-410 | 2019-07-04 | Performance Reporting | SA to confirm if updates to QiW website are completed. | WG (SA) | Closed |  | Changes which are awaiting testing which should be completed by end of next week.
SDF-412 | 2019-07-04 | Performance Reporting | The Welsh Government to pass feedback on workshops to QiW colleagues. | WG (SA) | Closed |  | Ongoing action - See SDF-410/ SDF-411) Quarterly update suggested to discuss extracts.
SDF-413 | 2019-07-04 | Post-16 | To clarify the meaning of “completed” in the Technical Completion Notes for Post-16. | WG (GE) | Closed | 2018-09-01 | From reviewing the completion notes, it appears that this is fairly self explanatory, so there is no intention to clarify unless further issues arise.
SDF-414 | 2019-07-04 | Attendance | GE to discuss registration issue where pupils start late with attendance policy colleagues. | WG (GE) | Closed | 2019-10-01 | Pupil registration is on the agenda for 17 October 2019
SDF-415 | 2019-07-04 | WNT/OPA | GE to discuss with colleagues about what online personalised assessment data, if any, could be included within the CTF. | WG (GE) | Closed | 2019-08-01 | Policy colleagues have confirmed that there is currently no intention for data to be made available in a format that can be exported from Hwb, and therefore, be included within CTFs.
SDF-415 | 2019-10-17 | SWAC | Issue with Post 16 with Welsh Bacc. The Dewi validation was correct, but the errors didn’t not remove so they have to re-upload. | JH M4 | Closed |  | Method 4 worked to ensure this would not happen and had fixed the issue but the validation was re-run without the previous errors being removed. JH agreed to investigate.
SDF-416 | 2019-07-04 | SDF | Capita ONE, Capita SIMS and Teacher Centre to send GE their release and development schedulese. | WG (GE) | Closed | 2019-08-13 | 13/09/2018 Ruth and Jim email update
SDF-416 | 2019-10-17 | SWAC | Qualified Teacher has an error with the Teacher number missing – QTS is status reorded as zero, this has also been covered in treating blank data. Rule 13036 - the rule should only trigger if QTS status is 1 and seemed to work correctly without any data in it | JH/RV | Closed |  | Agreed to send Method 4 a sample file
SDF-417 | 2019-07-04 | IMS | Suppliers to to be added to the IMS Calendar distribution list. | WG (CPD) | Closed | 2019-09-01 | Suppliers added to distribution list
SDF-417 | 2019-10-17 | SWAC | MJ Swansea agreed to share the outstanding additional 15 queries with the group, following the distribution of FAQ in which these queries were not covered | MJ/GT | Closed |  | GT agreed to share these wider.
SDF-419 | 2019-07-04 | TFSM/Transitional protection | The Welsh Government to share Ruth Vincent's email about the algorithm for use in identifying transitionally protected pupils for till system. | WG | Closed | 2019-07-15 | This was embedded and attached to the minutes of the 4 July 2019 meeting.
SDF-419 | 2019-10-17 | SWAC | Gav to check the max scores for the remaining numeracy reading tests will be likely to remain as 0-20 | GE | Closed | 2019-11-15 | Spec updated and score ranges confirmed
SDF-420 | 2019-10-17 | SWAC | GE to check if there is an issue with the validation rule for this years WNT, as it allows you to return last years data | GE | Closed | 2019-10-17 | Can't see an issues with validation and JHo confirmed there should be no effect on DEWi even if last year's data is included as it would just be ignored.
SDF-422 | 2019-10-17 | EOTAS | RV volunteered to see why they abandoned collecting data on alterative provision in England to share with KB. | Capita (RV) | Closed | 2020-01-27
SDF-425 | 2020-02-06 | SWAC | The Welsh Government to introduce <FTE> when reviewing the SWAC collection for November 2020. | WG (GE/GT) | Closed
SDF-426 | 2020-02-06 | SWAC | GT to set out options for recording SENCo’s for discussion in SWAC workshop. | WG (GT) | Closed
SDF-436 | 2020-03-05 | P16 | The Welsh Government to add a new <DiscountCode> data element to the Post-16 collection for autumn 2020 | WG (GE) | Closed
SWAC-001 | 2018-02-22 | SWAC | Capita to send WG list of subjects | Capita | Closed
SWAC-002 | 2018-06-26 | SWAC | GTh to consider whether to add an identifier to data field XML tags so that it can be easily seen whether it is LA or school supplied data. | WG/GTh | Closed |  | In new version of spec
SWAC-003 | 2018-06-26 | SWAC | WG to consider dates for 2019 collection | WG | Closed |  | Closed - 19th November SWAC opens
SWAC-004 | 2018-06-26 | SWAC | WG to work with equality division to agree gender categories. | WG | Closed |  | Ongoing - needs a WG approach, discussions happening shortly Agreed a position for Wales that now works with CTF.
SWAC-005 | 2018-06-26 | SWAC | JA offered to send a mock up of the staff CTF structure to the SWAC team. | Capita | Closed |  | Not for this first phase. DfE to explore this and come back to us.
SWAC-006 | 2018-06-26 | SWAC | WG/MJ to look at building structure of supply data to be collected | WG/MJ | Closed |  | Revised in spec
SWAC-007 | 2018-06-26 | SWAC | WG to review spec to ensure consistency in recording of true / false fields. | WG | Closed
SWAC-008 | 2018-06-26 | SWAC | WG to review lesson medium options | WG | Closed
SWAC-009 | 2018-06-26 | SWAC | WG to look at how completer hours are used once collected and whether data still needs to be collected for all collections. | WG | Closed |  | This information is required by ONS and will be looked at further.
SWAC-010 | 2018-06-26 | SWAC | WG to work with MJ to replace ‘SEN co-ordinator’ with ‘Additional Roles’ and provide definitive list of roles to be included in census. | WG | Closed |  | 1 repeating container for all additional roles
SWAC-011 | 2018-06-26 | SWAC | Staff CTF structure to WG | Capita | Closed |  | (Same as action 005)
SWAC-012 | 2018-06-26 | SWAC | Outline the timescales as soon as possible. | WG | Closed |  | Confirmed in SDF and SWAC workshop.
SWAC-013 | 2018-06-26 | SWAC | v0.3 of the Specification to be released to suppliers. | WG¦ | Closed |  | released 21/09/2018
SWAC-014 | 2019-02-07 | SWAC | GT to consider content of next SWAC bulletin | WG | Closed |  | Released in Feb
SWAC-015 | 2019-02-07 | SWAC | WG to release a draft version of the completion notes and privacy notice by the end of March | WG | Closed |  | 07/03/19 - to be released soon, being worked on currently // 04/06/19 - these draft versions have been circulated with LAs and finalised versions should be published this month
SWAC-016 | 2019-02-07 | SWAC | MJ to invite WG colleagues to workshop | MJ | Closed
SWAC-017 | 2019-03-07 | SWAC | WG will look at options and draw up plan in relation to pilots. | WG | Closed | 2019-07-04 | On agenda for 4 July 2019 meeting and pilot details circulated in email.